## Sheet1
S/N | LOCATION | MRF NUMBER | REQUEST DATE | YEAR | REASON FOR REQUEST | SERVICE\MATERIAL | DISCIPLINE | MRF STATUS | CONTRACT / CALL OFF NO | REMARKS
1 | OGBOIBIRI | SAR-001-2025 | 2025-01-02 | 2025 | REPLACEMENT OF FAULTY TURBO CHARGER | TURBO CHARGER | MECHANICAL | APPROVED QUOTATION |  | Emeka Okafor
2 | BRASS TERMINAL | SAR-002-2025 | 2025-01-02 | 2025 | TO REPLACE CORRODED 6 INCH DIESELLINE IN BRASS | ELECTRODE E6010 X3.2MM, E7018 X 3.2 MM, STEEL POWER BRUSH CUP TYPE…ETC | ROTATING EQUIPMENT | AWAITING UPDATE EMEKA |  | Emeka Okafor
3 | BRASS TERMINAL | SAR-003-2025 | 2025-01-02 | 2025 | OGB DP 5TBG SCALE REMOVAL | 1/2 NIPPLE, 6000 PSL 1/2 CHECK VALVES, 1/4'' TUBBING, 3/8'' COUPLING | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
4 | BRASS TERMINAL | SAR-004-2025 | 2025-01-04 | 2025 | 30KVA UPS FOR USE AT THE DCS CENTRE BRASS CONTROL ROOM | 30KVA UPS FOR DCS CENTRE | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
5 | BRASS TERMINAL | SAR-005-2025 | 2025-01-05 | 2025 | REPALCEMENT GENERATOR STARTER BATTERIES AND M-PANEL BATTERY FOR RCE GEN-3 | 200AH 12V CATERPILLAR BATTERY AND 18AH 12V, M PANEL BATTERY | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
6 | BRASS TERMINAL | SAR-006-2025 | 2025-01-08 | 2025 | REPALCEMENT OF FAULTY SENSOR OF NK-2 STATIONARY COMPRESSOR IN THE TANK FARM | REPLACEMENT OF FAULTY SENSOR OF NK-2 STATIONARY COMPRESSOR IN THE TANK FARM | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
7 | BRASS TERMINAL | SAR-007-2025 | 2025-01-11 | 2025 | REPLACEMENT OF FAULTY PARTS OF RCE GEN-1 IN THE TANK FARM | IGNITION BOX MC 950, 5 PIN DOIDE RELAY, 5 PIN BASE FOR DIODE RELAY..ETC | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
8 | BRASS TERMINAL | SAR-008-2025 | 13-1-2025 | 2025 | REPLACEMENT OF PHASE -1 FAULTY PARTS OF RCE GEN-1 AND GEN-2 IN THE TANK FARM | CAM PICKUP, CAM PICKUP CABLE HARNESS..ETC | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
9 | BRASS TERMINAL | SAR-009-2025 | 2025-01-12 | 2025 | REPLACEMENT OF BAD FIRE-PUMP BATTERIES, MOBILE AIR COMPRESSOR,OTM PUMP AND COMMUNITY GEN TO CLOSE OUT SAFETY CONCERNS IN OBAMA F/S | 12V, 200AH CAT BATTERY, 12V 75AH CAT BATTERY | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
10 | BRASS TERMINAL | SAR-010-2025 | 2025-01-14 | 2025 | REPLACEMENT OF CRASHED SCADA SERVER | M SERIES MQ CONTROLLER, DELL RACK SERVER | INSTRUMENT | AWAITING UPDATE EMEKA |  | Emeka Okafor
11 | BRASS TERMINAL | SAR-011-2025 | 2025-01-15 | 2025 | REPLACEMENT OF FAULTY ETHERNET SWITCH FOR SCAD/OMNI COMMUNICATION | ETHERNET SWITCH FOR SCAD/OMNI COMMUNICATION, MAKE: D-LINK. TYPE: DGS-1100-08P AND SIXNET ETHERNET SWITCH: MAX. RATING: 175mA @30VDC | INSTRUMENT | AWAITING UPDATE EMEKA |  | Emeka Okafor
12 | BRASS TERMINAL | SAR-012-2025 | 2025-01-18 | 2025 | PHASE 1- REQUEST TO FORSTALL UNFORSEEN FAILURE OF THE SERVOMOTOR(ACTUATOR) FOR GEN-1 AND GEN-3 | SERVOMOTOR | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
13 | TEBIDABA | SAR-013-2025 | 2025-01-18 | 2025 | TO RESTORE FIRE-FIGHTING SYSTEM BY PUTTING BACK SUBMERSIBLE PUMPS 1 AND 2 IN SERVICE | 4-POLE, 100AMP MINIATURE CIRCUIT BREAKER, SCOTCH CAST INLINE RESIN KIT, A-91 SERIES…ETC | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
13 | BRASS TERMINAL | SAR-014-2025 | 2025-01-20 | 2025 | REPLACEMENT OF VOLTAGE AND FREQUENCY CONTROLS FOR BRASS RESIDENTIAL EDG THAT ARE DUE FOR CHANGE | VOLTAGE CONTROL G AND SPEED/FREQUENCY CONTROL | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
14 | OGBOINBIRI | SAR-015-2025 | 2025-01-21 | 2025 | REPLACEMENT OF WEAKENING BATTERIES FOR EDG IN OGB | ALKALINE BATTERIES | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
15 | BRASS TERMINAL | SAR-016-2025 | 2025-01-20 | 2025 | REPLACEMENT OF WATER FILLING VALVE FOR RCE PHASE-1 GEN 2 | WATER FILLING VALVE | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
16 | BRASS TERMINAL | SAR-017-2025 | 2025-01-21 | 2025 | PARTS FOR RCE PHASE 1 GEN-2 TO PREVENT SUDDEN SHUTDOWN | ORINGS / GASKETS AND EXHAUST MANIFOLD | MECHANICAL | AWAITING UPDATE EMEKA |  | AWAITING UPDATE EMEKA
17 | BRASS TERMINAL | SAR-018-2025 | 2025-01-22 | 2025 | PROVISION OF POWER SUPPLY FROM SWITCHGEAR ROOM TO BRASS LNG RESIDENTIAL | 3C X 150MM XLPE CABLE | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
18 | BRASS AND OGB | SAR-019-2025 | 2025-01-25 | 2025 | DCS SPARES FOR DCS OPERATIONS IN BRASS AND OGB CONTROL ROOMS | DCS SPARES AND ACCESSORIES | INSTRUMENT | AWAITING QUOTATION |  | AMEZHINIM ODOYI
19 | BRASS | SAR-020-2025 | 2025-02-04 | 2025 | REPLACEMENT SPARES FOR ANNUAL RE-CERTIFICATION OF BRASS METERING SKID | ROSEMOUNT 3144P TEMPERATURE TRANSMITTER, CLIF MOCK SAMPLE CONTROLLER: 24VDCac50/60hz…ETC | INSTRUMENT | AWAITING QUOTATION |  | AMEZHINIM ODOYI
20 | BRASS | SAR-021-2025 | 2025-03-12 | 2025 | TO REPLACE BAD BATTERIES FOR PRODUCTION GENEERATORS AND FIRE PUMPS AT BRASS AND FLOW STATIONS IN ORDER TO CLEAR PENDING UNSAFE CONDITIONS | 101-400, 12V,PREMIUM HIGH OUTPUT, DRY BATTERY, 153-5710, 12V, PREMIUM, HIGH OUTPUT DRY BATTERY…ETC | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
21 | OGBOINBIRI | SAR-022-2025 | 2025-02-08 | 2025 | REPALCEMENT OF INSTRUMENT CONSUMABLES | 3/8 UNION T, 1/2T X 3/4 NPT….ETC | INSTRUMENT | MATERIALS SUPPLIED IN-HOUSE(WAREHOUSE) |  | CHUKWU DANIEL
22 | BRASS | SAR-023-2025 | 2025-02-06 | 2025 | TO RSTORE FLAME CUTTING GASES IN SAR | FILLED OXYGEN GAS, FILLED ACETYLENE GAS | GMC | QUOTATION PENDING APPROVAL |  | Emeka Okafor
23 | BRASS | SAR-024-2025 | 2025-02-10 | 2025 | TO REPLACE VANDALIZED EARTH CABLES ON ALL PRODUCTION TANKS IN BRASS TERMINAL | 70MM2 EARTH CABLE, 70MM2 FERRULE, 70MM2 TERMINAL LUGS..ETC | GMC | AWAITING UPDATE EMEKA |  | Emeka Okafor
24 | OGBOINBIRI | SAR-025-2025 | 2025-02-16 | 2025 | URGENT REPLACEMENT OF EXPLOIT LINE TRANSMITTERS(PRESSURE & FLOW) | PRESSURE TRANSMITTER AND FLOW TRANSMITTER | INSTRUMENT | AWAITING QUOTATION |  | AMEZHINIM ODOYI
25 | OGBOIBIRI | SAR-026-2025 | 2025-02-18 | 2025 | REPLACEMENT OF FAULTY MESH 20 FOR STREAM 1 STRAINER | MESH 20 | MECHANICAL | AWAITING QUOTATION |  | CHUKWU DANIEL
26 | CLOUGH CREEK | SAR-027-2025 | 2025-02-19 | 2025 | ROUTINE SERVICING OF CLOUGH CREEK EDG | OIL(DEO-15W40) OIL FILTERS, WATER SEPARATOR FILTER AND OIL FILTER | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
27 | OBAMA | SAR-028-2025 | 2025-02-19 | 2025 | ROUTINE SERVICING OF OBAMA CG-2 | OIL(NGEO ADVANCE 40) OIL FILTERS, MULTIPURPOSE GREASE | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
28 | BRASS | SAR-029-2025 | 2025-02-19 | 2025 | REPALCEMENT OF DRIVE BELTS FOR INDUSTRIAL EDG AND MILLER WELDING MACHINE IN BRASS TERMINAL | DRIVE BELTS | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
29 | OBAMA | SAR-030-2025 | 2025-02-22 | 2025 | REPLACEMENT PART FOR OBAMA DELIVERY PUMP-3 | COMPLETE MECHANICAL SEAL ASSEMBLY, REPAIR KIT AND COUPLING | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
30 | BRASS | SAR-031-2025 | 2025-03-02 | 2025 | BATTERIES FOR BRASS METER BANK AND BOOSTER STATIONS ROTORK IQ(EMV) VALVES | 9V DURACELL BATTERY (ORIGINAL) OR EQUIVALENT | INSTRUMENT | AWAITING UPDATE EMEKA |  | Emeka Okafor
31 | BRASS | SAR-032-2025 | 2025-03-04 | 2025 | REPLACEMENT OF BURNT PUMP AND ONE TO BE AS SPARE | DAB PUMP | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
32 | TEBIDABA | SAR-033-2025 | 2025-03-12 | 2025 | REPLACEMENT OF BAD 3-INCH FLOW METER(OIL MEASUREMENT) BATTERY ON THE TEST SEPARATOR | CAMERON BATTERY 3.6 VDC NOMINAL, CURRENT LIMITED TO 80mA MAX | MECHANICAL | AWAITING QUOTATION |  | AMEZHINIM ODOYI
33 | BRASS | SAR-034-2025 | 2025-03-12 | 2025 | FABRICATION OF NEW AIR RUBBER AT THE OLD API SKIMMER UNIT | 3/4" SCH 80 GALVAN PIPE X 6 METERS, 1'' SCH 80 GALVNIZED PIPE X 6 METERS | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
34 | BRASS | SAR-035-2025 | 2025-03-13 | 2025 | REPAIR OF CORRODED DOCK GATES 1 AND 2 AT BRASS MAIN GATE | 75MM X 75MM X 3MM SQUARE PIPE, 7.5MM X 3MM FLAT BAR, RED OXIDE PAINT…ETC | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
35 | OGBOIBIRI | SAR-036-2025 | 2025-03-17 | 2025 | THE VALVES HAVE FAILED AND THERE IS NO SPARE | 16* X 600 CHECK VALVE FOR HPC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
36 | BRASS | SAR-037-2025 | 2025-03-18 | 2025 | REPLACEMENT OF REMOVED BATTERIES FROM GEN-1 | DRY CELL STARTER BATTERY, 200AH, 12V | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
37 | OGBOINBIRI | SAR-038-2025 | 2025-03-26 | 2025 | PARTS NOT AVAILABLE AND URGENTLY NEEDED | POWER SUPPLY FOR PLC RACK, SOLENOID VALVE, ELECTRIC FAN MOTOR FOR GTB-B, SET OF BATTERIES FOR LP/M-A/B | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
38 | OGBOINBIRI | SAR-039-2025 | 2025-03-26 | 2025 | THESE ITEMS OR PUMP PARTS ARE FAULTY AND DAMAGED, NEEDS TO BE REPLACED | WATER PUMP, WATER PUMP PULLEY, OIL SEAL PULLEY, CRANK SHAFT OIL SEAL, OIL PUMP | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
39 | TEBIDABA | SAR-040-2025 | 2025-03-25 | 2025 | REPLACEMENT OF BAD CHOKE VALES ON WEEL HEAD TEB 9 AND TEB 12 | 3-1/8'' X 5000#RJ CHOKE VALVE | MECHANICAL | AVAILABALE IN THE WAREHOUSE |  | Emeka Okafor
40 | OBAMA | SAR-041-2025 | 2025-03-25 | 2025 | GREASING OF VALVES AT THE ARRIVAL MANIFOLD | GADUS - HIGH PERFORMANCES MULTI PURPOSE EXTREME HIGH PRESSURE GREASE | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
41 | OGBOINBIRI | SAR-042-2025 | 2025-04-07 | 2025 | GREASING OF STIFF VALVES IN THE PLANT | GREASE MU EP 2KG 18 SE | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
42 | OGBOINBIRI | SAR-043-2025 | 2025-04-07 | 2025 | REQUEST FOR FAULTY MECHANICAL SEAL OF CLOSED DRAIN PUMP | 50MM-A/Q-B/Q2/V/M/G | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
43 | BRASS | SAR-044-2025 | 2025-04-09 | 2025 | REPLACEMENT OF FAULTY HELIPAD FLOOD LIGHT | DOWNING SEALED BEAM HELIPAD SURFACE FLOOD LAMP 24VAC | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
44 | BRASS | SAR-045-2025 | 2025-04-17 | 2025 | REQUEST FOR LOADING REPORT ITEMS | CONTINOUS FEED COMPUTER PAPER FANFOLD, RIBBON CATRIDGE AND TONER | INSTRUMENT | AWAITING UPDATE EMEKA |  | Emeka Okafor
45 | OGBAINBIRI | SAR-046-2025 | 2025-04-29 | 2025 | PROCUREMENT OF SOLENOID FOR GAS COMPRESSOR HP-A | SOLENIOD | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
46 | BRASS | SAR-047-2025 | 2025-04-19 | 2025 | REQUEST FOR CONSTRUTION CONSUMABLES | COMPLETE OXYGEN/ACETYLENE CUTTING SET | INSTRUMENT | AWAITING UPDATE EMEKA |  | Emeka Okafor
47 | CLOUGH CREEK | SAR-049-2025 | 2025-04-23 | 2025 | REQUEST TO REPLACE FAULTY MOBILE AIR COMPRESSOR START MODULE | MOBILE AIR COMPRESSOR STARTER MODULE | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
48 | BRASS | SAR-050-2025 | 2025-04-25 | 2025 | MATERIAL NEEDED FOR THE INSTALLATION OF THE NEW DOCK DISTRIBUTION PANEL | 4X50 MM2 PWA/SWA PVC INSULATED ARMOUND CABLE | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
49 | BRASS | SAR-051-2025 | 2025-05-02 | 2025 | REQUEST TO REPLACE FAULTY FAULTY UPS MAINS CIRCUIT BREAKER | CIRCUIT BREAKER | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
50 | BRASS | SAR-052-2025 | 2025-05-02 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEMS | IG55 GAS CYLINDER, CONTROL PANEL, BATTERY, RELEASE SWITCHES…ETC | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
51 | CLOUGH CREEK | SAR-053-2025 | 2025-05-02 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEMS | IG55 GAS CYLINDER, CONTROL PANEL, BATTERY, RELEASE SWITCHES…ETC | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
52 | OBAMA | SAR-054-2025 | 2025-05-02 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEMS | IG55 GAS CYLINDER, CONTROL PANEL, BATTERY, RELEASE SWITCHES…ETC | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
53 | OGBOINBIRI | SAR-055-2025 | 2025-05-02 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEMS | IG55 GAS CYLINDER, CONTROL PANEL, BATTERY, RELEASE SWITCHES…ETC | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
54 | TEBIDABA | SAR-056-2025 | 2025-05-02 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEMS | IG55 GAS CYLINDER, CONTROL PANEL, BATTERY, RELEASE SWITCHES…ETC | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
55 | CLOUGH CREEK | SAR-057-2025 | 2025-05-03 | 2025 | REQUEST TO REPLACE FAULTY EDG CHARGING ALTERNATOR | 45A, 24V CHARGE ALTERNATOR | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
56 | BRASS | SAR-058-2025 | 2025-05-03 | 2025 | REQUEST TO REPLACE FAULTY BEARINGS FOR THE OVERHAUL OF E-MOTOR AND GREEN DRAIN PUMP | SKF 6316/C3 BEARINGS AND SKF 6307 BEARINGS | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
57 | BRASS | SAR-059-2025 | 2025-05-09 | 2025 | CABLE TO TAKE POWER SUPPLY FROM BARGING SUBSTATION TO THE DISTRIBUTION PANEL AND TO LINK POWER SUPPLY TO THE EXISTING HOUSE BOAT DISTRIBUTION BOX | PVC INSULATED AMOURED CABLE 4X50MM2 AND 4X35MM2 PWA/SWA PVC | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
58 | BRASS | SAR-60-2025 | 2025-05-09 | 2025 | TO PROVIDE CONSTANT POWER SUPLY FROM BRASS SWITCH GEAR ROOM TO BRASS LNG RESIDENTIAL AREA | 3X10mm2 AMMOURED CABLE, 11KV RAYCHEM KIT, 600mm x 300mm concrete slabs | GMC | QUOTATION PENDING APPROVAL |  | Emeka Okafor
59 | OGBOINBIRI | SAR-061-2025 | 2025-06-10 | 2025 | REPLACEMENT OF FAULTY MESH 20 FOR STREAM 1 STRAINER | MESH 20 | INSTRUMENT | QUOTATION PENDING APPROVAL |  | Emeka Okafor
60 | OGBOINBIRI | SAR-062-2025 | 2025-06-10 | 2025 | REPLACEMENT OF FLAME OUT SWITCH FOR LP-MP COMPRESSORS | FLAME OUT SWITCH | INSTRUMENT | QUOTATION PENDING APPROVAL |  | Emeka Okafor
61 | OBAMA | SAR-063-2025 | 2025-05-22 | 2025 | REPLACEMENT OF FAULTY AVR ON CG-2 GENERATOR | CATERPILLAR AVR(VRS) POWER SHUNT EXCITED | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
62 | OBAMA | SAR-064-2025 | 2025-05-22 | 2025 | SERVICING/TOPPING OF CG-2 GENERATOR | LUBE OIL FOR SERVICING/TOPPING-(NGEO ADVANCED 40) 2DRUMS(400L) | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
63 | OBAMA | SAR-065-2025 | 2025-05-23 | 2025 | REPLACEMENT OF FAULTY POTENTIAL TRANSFORMER OF CG-2 GENERATOR | POTENTIAL TRANSFORMER(PT)CAT | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
64 | BRASS | SAR-066-2025 | 2025-05-23 | 2025 | RADIATOR FAN MOTORS TO BE REPALCED FOR NEW RADIATORS TO BE USED DURING PHASE- 1 ENGINE CHANGEOUT | RADIATOR FAN MOTOR | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
65 | OBAMA | SAR-067-2025 | 2025-05-26 | 2025 | MATERIALS NEEDED FOR PIRIGBENE 2 AND 4 MANIFOLD ACTIVITIES | 75mm x 75mm ANGLE IRON, 1 AND HALF INCHES SCH 40 GALVANIZED PIPES, ..ETC | GMC | QUOTATION PENDING APPROVAL |  | Emeka Okafor
66 | OBAMA | SAR-068-2025 | 2025-05-26 | 2025 | MATERIAL IS FOR THE REPLACEMENT OF A FAULTY ONE ON THE DANIEL ORIFICE BOX. | PLATE CARRIER FOR DANIEL ORIFICE BOX14” x 300# | INSTRUMENT | QUOTATION PENDING APPROVAL |  | Emeka Okafor
67 | OGBOINBIRI | SAR-070-2025 | 2025-06-18 | 2025 | REQUEST FOR HIGH PROIRITY FIELD CALIBRATION INSTRUMENTS | FLUKE -754 PROCESS CALIBRATION WITH DOCUMENT FUNTION, EMERSON HEART 475 FIELD COMMUNICATOR | INSTRUMENT | QUOTATION PENDING APPROVAL |  | Emeka Okafor
68 | BRASS | SAR-071-2025 | 2025-06-19 | 2025 | REPLACEMENT OF FAULTY MECHANICAL SEALS FOR OGBOINBIRI | COMPLETE MECHANICAL SEAL WITH SERVICE KITS | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
69 | BRASS | SAR-072-2025 | 2025-06-19 | 2025 | REPLACEMENT OF BOP PLATFORM, GRATING AND ACCESS LADDER AT SP-1 OFFSHORE | GRATINGS, GALVANIZED PIPES AND FITTINGS | MECHANICAL | ASSIGNED TO HALLIDAY |  | Halliday
70 | OBAMA | SAR-073-2025 | 2025-06-28 | 2025 | REQUEST FOR PIRGBENE 2 & 4 MANIFOLD ACTIVITIES | 50MM X 50 MM X 5MM ANGLE IRON | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
71 | BRASS | SAR-074-2025 | 2025-07-04 | 2025 | TOOLS AND MATERIALS URGENTLY NEEDED IN THE SWAMP AREA FOR INSTRUMENTATION | WALLACE & TEIMAN ELECTRO-PNEUMATIC CALLIBRATOR, HYDRAULIC HAND TEST PUMP, MD+ PLUS CONTROLLEER…ETC | INSTRUMENT | QUOTATION PENDING APPROVAL |  | Emeka Okafor
72 | CLOUGH CREEK | SAR-075-2025 | 2025-07-22 | 2025 | MATERIALS URGENTLY NEEDED FOR CLOUGH CREEK EDG RESTORATION | FUEL PRIMING PUMP, FUEL FILTER | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
73 | OBAMA | SAR-076-2025 | 2025-07-24 | 2025 | 4nos 4”x900# RJ VALVES REQUIRED TO COMPLETE THE REPLACEMENT OF PASSING VALVES AT ARRIVAL MANIFOLD | 4nos 4”x900# RTJ BALL VALVE | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
74 | BRASS | SAR-077-2025 | 2025-07-24 | 2025 | 6 MONTHS SERVICING CONSUMABLES FOR BRASS EDG-1, BRASS EDG-2, OBAMA CG-2, OBAMA EDG-1 AND CLOUGH CREEK EDG-1. | LUBE OIL FOR SERVICING/TOPPING - CAT (DEO 15W-40)/OL-3E9840, OIL FILTER, FUEL FILTER, FUEL/WATER SEPARATOR…ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
75 | OBAMA | SAR-078-2025 | 2025-07-30 | 2025 | TO REPLACE PASSING VALVE FOR OBAMA 7LS STRING AT THE ARRIVAL MANIFOLD. | 4 " X 900# RTJ BALL VALVE | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
76 | BRASS | SAR-079-2025 | 2025-07-31 | 2025 | REPAIR OF TEBIDABA DELIVERY PUMP 2 | METAFLEX COUPLING COMPLETE, RADIAL BEARING, THRUST BEARING | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
77 | OBAMA | SAR-080-2025 | 2025-08-04 | 2025 | RECONSTRUCTION OF PIRIGBENE 2T XMAS TREE VALVE. | CCU VALVE 3-1/16” X 10,000lbs, 120mmX 60mmX6m U-CHANNEL, 150mmX150mmX6m H-Beam…..ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
78 | OBAMA | SAR-081-2025 | 2025-08-06 | 2025 | TO REPLACE BROKEN FFP 1( FIRE FIGHTING PUMP 1) SPACER FOR OBAMA F/S | GEAR SLEEVE-FLEX COUPLING | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
79 | BRASS | SAR-083-2025 | 2025-08-11 | 2025 | MATERIAL REQUEST FOR THE INSTALLATION OF TANK HATCH PUMPS IN BRASS TERMINAL. | Wilden Pump T8-51mm (2”) metal Pump Flowrate 617 LPM (163 GPM), 2” Hoses for pump suction and discharge, 1” Hoses for Air supply | INSTRUMENT | QUOTATION PENDING APPROVAL |  | Emeka Okafor
80 | OGBOINBIRI | SAR-084-2025 | 2025-08-16 | 2025 | MATERIAL REQUEST FOR THE MODIFICATION OF OGBOINBIRI METER BANK TO INSTALL INDORAMA METER. | 8” sch. 80 X 6-meter seamless C. S. pipe, 2” sch. 80 X 6 meters seamless C. S. pipe, 2” sch 80 BW 45 deg elbow…ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
81 | OGBOINBIRI | SAR-085-2025 | 2025-09-05 | 2025 | OLD BOOSTER PUMP C CIRCUIT BREAKER REPLACEMENT. | CIRCUIT BREAKER | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
82 | BRASS | SAR-086-2025 | 2025-08-22 | 2025 | REQUEST FOR THE BY-PASS MODIFICATION OF DEHYDRATION UNIT IN BRASS TERMINAL (MOC) | 10" X 150# RF W.N FLANGE, 12" X 300# RF W.N FLANGE, 8" X 150# W.N RF FLANGE…ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
83 | BRASS | SAR-087-2025 | 2025-08-24 | 2025 | TO REPLACE DEFECTIVE BEARING FOR OGP 200KW BOOSTER PUMP B. | SKF 6316-2Z/C3 BEARING | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
84 | BRASS | SAR-088-2025 | 2025-09-01 | 2025 | INSTALLATION OF FOUR NEW AUTO TRANSFORMERS SUPPLIED BY POD. | 1 X 185 STRANDED PVC/SWA INSULATED CABLES IN METERS, 1 X185mm² X 10 CABLE LUGS…..ETC | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
85 | BRASS | SAR-089-2025 | 2025-09-01 | 2025 | CONSUMABLES FOR SERVICING OF RESIDENTIAL & POWER STATION EDGs. | OIL FILTER, FUEL FILTER, WATER SEPARATOR, DEO CAT…....…ETC | CONSUMABLES | QUOTATION PENDING APPROVAL |  | Emeka Okafor
86 | BRASS | SAR-090-2025 | 2025-09-01 | 2025 | CONSUMABLES FOR 3KV SWITCHGEAR PANEL. | MV FUSES; Un = 3.6KV, In = 100 A, I1= 50KATYPE CMF, STRIKER = 80N (medium), 10ft x 4.31`` GALVANIZED CABLE TRUNK | CONSUMABLES | QUOTATION PENDING APPROVAL |  | Emeka Okafor
87 | BRASS | SAR-091-2025 | 2025-09-06 | 2025 | TO FIX FAULTY NEW API PUMP P11A. | PUMP DATATYPE: SPISIZ: 3 X 3 X 9SERIAL NUMBER: 121000211-2YEAR: 2014RPM: 2960 | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
88 | BRASS | SAR-092-2025 | 2025-09-08 | 2025 | ADDITIONAL MATERIALS FOR THE MODIFICATION OF DEHYDRATION UNIT IN BRASS BASED ON MOC. | 4” x 150RF Globe Valve, 12” X 150RF Spiral Wound Gaskets, 4” X 150RF Spiral Wound Gaskets….....ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
89 | BRASS | SAR-093-2025 | 2025-09-11 | 2025 | MATERIALS FOR CONSTRUCTION MAINTENANCE WORKSHOP USE | Welder hand gloves (American safety- red), Fitter hand groves (Leather fitter hand gloves)…...ETC | CONSUMABLES | QUOTATION PENDING APPROVAL |  | Emeka Okafor
90 | BRASS | SAR-094-2025 | 15--SEP-25 | 2025 | MATERIALS FOR SERVICING OF OBAMA CG-2 | OIL FILTERS, LUBE OIL (NGEO ADVANCED 40) | CONSUMABLES | QUOTATION PENDING APPROVAL |  | Emeka Okafor
91 | CLOUGH CREEK | SAR-095-2025 | 2025-09-21 | 2025 | CONSUMABLES FOR SERVICING OF CLOUGH CREEK EDG. | OIL FILTER, WATER SEPARATOR, LUBE OIL FOR SERVICING/TOPPING - CAT (DEO 15W-40)/OL-3E9840…..ETC | CONSUMABLES | QUOTATION PENDING APPROVAL |  | Emeka Okafor
92 | OBAMA | SAR-096-2025 | 2025-09-24 | 2025 | MATERIAL REQUEST FOR THE RESTORATION OF OBAMA CG-2 | CYLINDER HEADS, CYLINDR HEADS GASKET KIT, SPARK ARRESTOR, ENGINE SPEED/TIMING SENSOR…......ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
93 | BRASS | SAR-097-2025 | 2025-10-05 | 2025 | MATERIAL REQUEST TO REPLACE FAULTY INTRINSICALLY SAFE POWER SUPPLY CARD FOR RTU-3. | Delta V I.S. I/O POWER SUPPLYInput voltage; 24Vdc nominalOutput current; 5A | INSTRUMENT | QUOTATION PENDING APPROVAL |  | Emeka Okafor
94 | BRASS | SAR-098-2025 | 2025-10-14 | 2025 | MATERIAL REQUEST TO REPLACE FAULTY SPIRAL WOUND GASKET FOR THE OUTLET OF TP-9. | 20" X #300 RF SPIRAL WOUND GASKET | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
95 | OBAMA | SAR-099-2025 | 2025-10-21 | 2025 | REPLACEMENT OF FAULTY CIRCUIT BREAKER FOR OBAMA CG-2 | MERLIN GERIN M16H2 MASTERPACTCIRCUIT BREAKER 1600A | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
96 | OBAMA | SAR-101-2025 | 2025-10-25 | 2025 | REPLACEMENT OF UNSERVICEABLE FIRE-FIGHTING PUMPS IN SAR | REDDY-BUFFALOES PUMPH – SPLITCASESIZE/TYPE – 6 X 6LDFRATED BHP – 207 (154.46 HP) | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
97 | BRASS | SAR-102-2025 | 2025-10-24 | 2025 | REPLACEMENT OF FAULTY PARTS DURING RCE ENGINE CHANGE-OUT | DUNGS GAS PRESSURE REGULATOR FRS 5080, DUNGS GAS SOLENOID VALVE DMV 5080 | INSTRUMENT | QUOTATION PENDING APPROVAL |  | Emeka Okafor
98 | BRASS | SAR-103-2025 | 2025-10-25 | 2025 | CORRECT SPECIFICATION OF BOP BOAT LANDING PLATFORM OFFSHORE GRATING | 3FT X 20FT FIBREGLASS REINFORCED PLASTIC OFFSHORE GRATING | GMC | QUOTATION PENDING APPROVAL |  | Emeka Okafor
99 | BRASS | SAR-104-2025 | 2025-10-28 | 2025 | NEW AUTO TRANSFORMER ROOF RAFTERS AND DOORS FABRICATION | U-CHANNEL 80MM X 40MM X 7MM X 6MTS LONG, 90 DEGREE ANGLE BAR. 50MM X 50MM X 5MM X 6MTS LONG…...ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
100 | OBAMA | SAR-105-2025 | 2025-10-29 | 2025 | TO FABRICATE SPOOL FOR TEMPORARY REPLACEMENT OF 14" X 300# RF DOB | SO FLANGE ND 14" X 300# RF, PIPE ND 14’’ SCH 40., SW Gasket ND 14" X 300# RF, STUD BOLT WITHh NUT ND 1. 1/8 X 188. | GMC | QUOTATION PENDING APPROVAL |  | Emeka Okafor
101 | TEBIDABA | SAR-106-2025 | 2025-10-30 | 2025 | TO FABRICATE THE PIPING NETWORK OF CONDENSATE AND DIAPHRAGM PUMPS | Ø1" X 6MTS SCH 80 GALVISED PIPE (BOTH ENDS THREADED), Ø1" X SCH 80 NPT UNION CONNECTOR….ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
102 | TEBIDABA | SAR-107-2025 | 2025-10-30 | 2025 | TO REPLACEMENT OF PASSING VALVES AT THE ARRIVAL MANIFOLD AND REPAIR THE RAIL OF THE OVERHEAD MANUAL CRANE FOR BOOSTER PUMPS INSTALLATION | ARRIVAL MANIFOLD VALVES REPLACEMENT,Ball Valve ND 4’’ X 900#RJ – SPEC- VB-516-AG-2C1-RJ (F.B-split body)…ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
103 | BRASS | SAR-108-2025 | 2025-11-01 | 2025 | TO FABRICATE BRASS SULZER PUMP PROPOSED BY-PASS LINE | BALL VALVE ND 20" X 300#RF, WN FLANGE ND 20" X 300#RF SCH 40, STUD BOLT WITH NUTS ND 1-1/4" X 222…..ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
104 | OGBOINBIRI | SAR-109-2025 | 2025-11-06 | 2025 | MAINTENANCE OF OGBOINBIRI GAS PLANT DELIVERY PUMP JTN3 (8 STAGES) | Left impeller, Impeller wear ring, Suction side, Impeller wear ring,Series….....ETC | MECHANICAL | QUOTATION PENDING APPROVAL |  | Emeka Okafor
105 | OBAMA | SAR-110-2025 | 2025-11-09 | 2025 | REPLACEMENT OF FAULTY WOODWARD 2301A (LOAD SHARING AND SPEED CONTROL) | WOODWARD , LOW VOLTAGE, REV L, 2301A LOAD SHARING AND SPEED CONTROL. | ELECTRICAL | QUOTATION PENDING APPROVAL |  | Ikechukwu Iyeh
106 | CLOUGH CREEK | SAR-111-2025 | 2025-11-09 | 2025 | REPLACEMENT OF FAULTYFUEL HOSE | FUEL HOSESAE 100R17-8 12.5mm (1/2 inch)3000PSI MSHA 1C-40/26ENGINE | GMC | QUOTATION PENDING APPROVAL |  | Emeka Okafor