## Sheet2
Item | Asset | Mrf Number | Year | Request Date | Reason for Request | Service\Material | Discipline | Criticality | Status Notes | Status | Internal Reference | Action Pending | Vendor Name | Blanket Order Number | Call Off Number | Quotation | Quotation Approval Date | Quotation Amount USD | Quotation Amount EUR | Quotation Amount NGN | Estimated Delivery | Date of Delivery | Notes | Other
1 | OBOB | LAR-MCTE-001-2025 | 2025-01-02 | 2025 | TO CARRY OUT 500 HOURS ROUTINE PREVENTIVE MAINTENANCE SERVICE ON EMERGENCY GEN EDG-3 | OIL FILTER, FUEL FILTER, WATER SEPARATOR…ETC | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
2 | OBOB | LAR-MCTE-003-2025 | 2025-01-02 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT THE 1820 FIRE PUMP 1 | WAX PACKING GLAND | ROT EQUIP |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
3 | KWALE | LAR-MCTE-004-2025 | 2024-12-30 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT THE UNIT 6100 | MECHANICAL SEAL FOR BOOSTER PUMP 701 RE-KIT MATERIALS | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor | [7 empty] | 8050
4 | EBOCHA | LAR-MCTE-005-2025 | 2025-01-04 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT THE EOC-212 LIC-022B GUN BARREL LEVEL TRANSMIITER | VEGAPULS 62 RADAR SENSOR LEVEL TRANSMITTER | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
5 | KWALE | LAR-MCTE-006-2025 | 2024-12-30 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT THE UNIT 4100 | MECHANICAL SEAL FOR DELIVERY PUMP 2(INBOARD) RE-KIT MATERIALS | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
6 | KWALE | LAR-MCTE-007-2025 | 2024-12-30 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT THE UNIT 4100 | MECHANICAL SEAL FOR DELIVERY PUMP 2(INBOARD) RE-KIT MATERIALS | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
7 | OBOB | LAR-MCTE-008-2025 | 2025-01-02 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT THE 1820 FIRE PUMP 2 | WAX PACKING GLAND | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
8 | OBOB | L;AR-MCTE-009-2025 | 2025-01-02 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT THE 820 FIRE PUMP 1 | WAX PACKING GLAND | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
9 | OBOB | LAR-MCTE-010-2025 | 2025-01-11 | 2025 | TO ELIMINATE DIRTS IN THE LUBE OIL CIRCUIT | CLEANING OF LUBE OIL FAN COOLER HEAT EXCHANGER INTERNAL SYSTEM | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
10 | KWALE | LAR-MCTE-011-2025 | 2025-01-10 | 2025 | REVAMPING OF TOWER LIGHTS AND MAINTENANCE OF EXTERNAL LIGHTING SYSTEMS | 300W, IP65, 230V MUARVA LED FLOOD LIGHT FITTINGS, 198-264V A/C, 5A/80 uf ELECTRONIC PHOTO CONTROL KIT | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
11 | KWALE | LAR-MCTE-012-2025 | 2025-01-10 | 2025 | TO REPLACE FAULTY AND OBSELETE INTERNAL LIGHT FITTINGS IN OFFICES(PAF BUILDING, PO-2 OFFICE, WATCH POINT, ADMIN WALK WAY, CLUB HOUSE, GYM ROOM, MESS HALL, ABED STORES AND TV ROOM | 36W, 220-V-50HZ 2X2 CERTAFLUX LED BL PANEL LIHT FITTING AND 36W 220,-240V-50HZ LED ELECTRONIC DRIVER | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
12 | OBOB | LAR-MCTE-013-2025 | 2025-01-12 | 2025 | TO REPAIR FAULTY DOUBLE DIAPHRAGM PUMPS IN OSHIE, IDU, AKRI, FLOW STATIONS INCLUDING EOC AND OBOB GAS PLANT | DIAPHRAM | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
13 | OBOB | LAR-MCTE-015-2025 | 2025-01-13 | 2025 | OUT OF STOCK | TEMPERATURE TRANSMITTER AND ELEMENT SENSOR: PT100_385_4(4WIRES) RANGE 0-100 DEG C | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
14 | OBOB | LAR-MCTE-016-2025 | 2025-01-12 | 2025 | DUE FOR ROUTINE SERVICING, THE LAST SERVICING RUNNING HOURS ARE 5242 AND 4931 WHILE THE PRESENT RUNNING HOURS ARE 5624 AND 5241 | AIR FILTER, OIL FILTER, FUEL FILTER AND WATER SEPARATOR | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor
15 | OBOB | LAR-MCTE-017-2025 | 2025-01-12 | 2025 | TO CARRY OUT ROUTINE MAINTENANCE SERVICING. THE LAST SERVICING RUNNING HOURS WAS 4280 HRS, WHILE THE PRESENT RUNNING HOURS IS 4685 HOURS | ENGINE LUBE OIL, LUBE OIL FILTER, FUEL/WATER SEPARATOR, AIR FILTER AND COOLANT FILTER | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | Emeka Okafor | [5 empty] | Approved Quotation\2025\LAR 2025 A-Q\QOUTATION |  |  |  | N3116309.59
16 | OBOB | LAR-MCTE-018-2025 | 2025-01-15 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT UNIT 820-FP-01 | LOVE JOY MOTOR COUPLING SLEEVE FLEX, TYPE: RBW COUPLING SIZE, 1/5.37/87/219/87/180 COMPLETE COUPLING, SLEEVE FLEX, COUPLING NUEPRENE RUBBER | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
17 | EBOCHA | LAR-MCTE-019-2025 | 2025-01-19 | 2025 | FOR FABRICATION OF 1'' DRAIN LIONE UNIT 360A AT EBOCHA OIL CENTRE | WN FLANGE, 1'' X 600# RF, GATE VALVE, 1X800# RF, 90 DEG ELBOW, 1''X600# SW…ETC | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
18 | EBOCHA | LAR-MCTE-020-2025 | 2025-01-19 | 2025 | FOR FABRICATION OF METAL CHAMBER COVERS AT NEW BASE RESIDENTIAL AREA | ANGLE IRON, 50MM X50MMX5MM THICK, ROD, 12MM | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
19 | OBOB | LAR-MCTE-021-2025 | 2025-01-21 | 2025 | OUT OF STOCK | TEMPERATURE RTD'S | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
20 | OBOB | LAR-MCTE-022-2025 | 2025-01-23 | 2025 | TO BE USED UNIT 1620 | PROPANE | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
21 | OBOB | LAR-MCTE-023-2025 | 2025-01-26 | 2025 | TO REPLACE BURNT POWER CABLE, CTS AND PTS, CONTROL CABLES ON OMOKU COMMUNITY B 15MVA TRANSFORMER | 1 X 95MM2 33KV XLPE AMORED CABLE, 1 X 95MM2 33KV COLD SHRINK JOINTING KIT…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
22 | KWALE | LAR-MCTE-024-2026 | 2025-02-10 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT KWALE BOOSTER PUMP 701 | SKF - BEARINGS | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
23 | OBOB | LAR-MCTE-025-2025 | 2025-01-28 | 2025 | TO REPLACE BURNT INSTRUMENT CURRENT/VOLTAGE TRANSFORMERS AT COMMUNITY B 15MVA TRANSFORMER SUBSTATION | INSTRUMENT VOLATGE TRANSFORMER, INSTRUMENT CURRENT TRANSFORMER | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
24 | OBOB | LAR-MCTE-026-2025 | 2003-01-28 | 2025 | TO REPLACE FAULTY GENERATOR INCOMER (PT PROTECTION MCB) AT 240 SWITCHERGEAR ROOM | S2-H11 MCB AUXILLARY CONTACT (1N0+1NC), S 274 C3, 4P 400VAC, ICU-10KA CIRCUIT BREAKER | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
25 | OBOB | LAR-MCTE-027-2025 | 2025-01-26 | 2025 | TO REWIND ELECTRIC MOTORFOR SKRI AIR COMPRESSOR N0.2 | AKRI AIR COMPRESSOR MOTOR REWND | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
26 | OBOB | LAR-MCTE-028-2025 | 2025-01-26 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT THE OBOB 1800 GM01A AND 01B CHILLERS | YOVEL ORIGINAL (R22 FRE ON) REFRIGERANT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
27 | IDU | LAR-MCTE-029-2025 | 2025-01-29 | 2025 | TO CHANGE THE BATTERIES AT THE EASTLINE PUMP AND TO MAKE THE PUMP AVAILABLE AND FUNCTIONABLE | TO REPLACE IDU EASTLINE AND 2A FIRE PUMPS DEAD BATTERIES | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
28 | IRRI | LAR-MCTE-032-2025 | 2025-01-28 | 2025 | TO BE USED ON TEST SEPARATOR | CURRENT T O PRESSURE TRANSMITTER, FLOW ANALYSER, TURBINE METER…ETC | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
29 | OBOB | LAR-MCTE-033-2025 | 2025-02-04 | 2025 | REGULAR MAINTENANACE OF THE EXTERNAL/SECURITY LIGHTING SYSTEM | 500 WATT HALOGEN FLOOD LIGHT, 250 WATT MERCURY VAPOUR LAMP, 250 WATT MECURY VAPOUR CHOKE | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
30 | OBOB | LAR-MCTE-034-2025 | 2025-02-04 | 2025 | REGULAR MAINTENANACE OF THE EXTERNAL/SECURITY LIGHTING SYSTEM | 150 WATT LED FLOOD LIGHT, 10 AMP SINGLE POLE BREAKER, 3TF48 CONTACTOR…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
31 | OBOB | LAR-MCTE-035-2025 | 2025-02-04 | 2025 | REGULAR MAINTENANACE OF THE EXTERNAL/SECURITY LIGHTING SYSTEM | 4FT FLUORESCENT TUBE, CHOKE, STARTER….ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
32 | OBOB | LAR-MCTE-036-2025 | 2025-02-04 | 2025 | REGULAR MAINTENANACE OF THE EXTERNAL/SECURITY LIGHTING SYSTEM | 4FT FLUORESCENT TUBE, CHOKE, STARTER….ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
33 | OBOB | LAR-MCTE-037-2025 | 2025-02-03 | 2025 | REGULAR MAINTENANACE OF THE EXTERNAL/SECURITY LIGHTING SYSTEM | 200 WATT FLOODLIGHT, MERCURY VAPOUR LAMP, 250WATT COPPER CHOKE…ECT | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
34 | OBOB | LAR-MCTE-038-2025 | 2025-02-03 | 2025 | REGULAR MAINTENANACE OF THE EXTERNAL/SECURITY LIGHTING SYSTEM | 4FT FLUORESCENT TUBE, CHOKE, STARTER….ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
35 | EBOCHA | LAR-MCTE-039-2025 | 2025-02-04 | 2025 | OUT OF STOCK | COMPLETE ROTOR AND BLADE ASSEMBLY | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
36 | KWALE | LAR-MCTE-040-2025 | 2025-02-12 | 2025 | TO REPLACE FAULTY POWER CABLE WITH NEW ONE FOR BIRGAHI DP -1 PUMP ASSY | 3CX185MM2 ARMOURED CABLE | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
37 | OBOB | LAR-MCTE-041-2025 | 2025-02-10 | 2025 | FAULTY/NEEDS REPAIR | GEARBOX | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
38 | OBOB | LAR-MCTE-042-2025 | 2025-02-10 | 2025 | INSTALLATION AND REPLACEMENT | TURBINE MODULE | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
39 | OBOB | LAR-MCTE-043-2025 | 2025-02-10 | 2025 | CLEANING AND BALANCING | CC ROTOR CLEANING AND BALANCING | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
40 | OBOB | LAR-MCTE-044-2025 | 2025-02-10 | 2025 | REPLACED IN UNITS TAGGED THUS NEED FOR STOCK REPLENISHMENT AS STOCK LEVEL IS ZERO | POSITIVE DISPLACEMENT PUMP/HYDRAULIC PUMP | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
41 | OBOB | LAR-MCTE-045-2025 | 2025-02-10 | 2025 | FAULTY, NEED REPALCEMENT FOR SEIMENS-PROCESS SKID AND NONE IN STOCK | PMV POSITIONER INPUT; 20-100KPA, 3-15 PSI. | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
42 | KWALE | LAR-MCTE-046-2025 | 2025-02-13 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT KWALE BOOSTER PUMP 702 & 703 | MEACHANICAL SEAL REPAIRING KIT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
43 | EBOCHA | LAR-MCTE-047-2025 | 2025-02-14 | 2025 | TO CARRY OUT ROUTINE MAINTENANCE SERVICING. THE LAST SERVICING RUNNING HOURS WAS 786 HRS, WHILE THE PRESENT RUNNING HOURS IS 1411 | OIL FILTERS, FUEL FILTERS, ENGINE IOL AND AIR FILTER | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR |  |  |  |  | MANTRAC | Approved Quotation\2025\LAR 2025 A-Q\LAR-047-2025.pdf |  |  |  | NGN 4,065,605.79
44 | IRRI | LAR-MCTE-048-2025 | 2025-02-03 | 2025 | TO REPLACE DAMAGE PARTS ON CAT G3508A THIS IS DOWN | COMPLETE TOP CYLINDER, TOP CYLINDER GASKET, PISTON PIN, RING(TOP)….ETC | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR |  |  |  |  | MANTRAC | Approved Quotation\2025\LAR 2025 A-Q\LAR-MTCE-048-2025.pdf |  |  |  | NGN 29,682,006.57
45 | OBOB | LAR-MCTE-049-2025 | 2025-02-17 | 2025 | FOR REGULAR MAINTENANCE OF EXTERNAL/SECURITY LIGHTING SYSTEM | 200W LED FLOOD LIGHT, 300W LED FLOOD LIGHT…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
46 | IRRI | LAR-MCTE-050-2025 | 2025-02-10 | 2025 | FOR MONITORING SYSTEM PERFORMANCE ACCURATELY AT THE PLANT AND WELL-HEAD OPERTION | 0 TO 150 PIS 1/2'' NPT, 0 TO 300 PIS 1/2'' NPT…...ETC | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
47 | OBOB | LAR-MCTE-051-2025 | 2025-02-18 | 2025 | WELDING MACHINE USE | 75 AMP SOLITE BATTERY | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
48 | IRRI | LAR-MCTE-052-2025 | 2025-02-17 | 2025 | MATERIALS TO MAINTAIN AND KEEP THE UNITS IN FUNCTIONAL STATUS | GAS REGULATOR, FLAME DETECTOR SENSOR, DIFFERENTIAL PRESSURE SWITCH…...ETC | INSTRMENT |  | AWAITING QUOTATION | AMEZHINIM ODOYI
49 | AKRI | LAR-MCTE-053-2025 | 2025-02-18 | 2025 | FOR THE MAINTENANCE OF THE INTERNAL/EXTERNAL SECURITY LIGHTS IN AKRI F/S | 200W LED FLOOD LIGHT, 100W LED FLOOD LIGHT, 4FT LED FLUORESCENT TUBE…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
50 | OSHIE | LAR-MCTE-054-2025 | 2025-02-18 | 2025 | FOR THE MAINTENANCE OF THE INTERNAL/EXTERNAL SECURITY LIGHTS IN OSHIE F/S | 200W LED FLOOD LIGHT, 100W LED FLOOD LIGHT, 4FT LED FLUORESCENT TUBE…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
51 | OBOB | LAR-MCTE-055-2025 | 2025-02-18 | 2025 | FOR THE MAINTENANCE OF THE INTERNAL/EXTERNAL SECURITY LIGHTS IN GRP OBIE | 200W LED FLOOD LIGHT, 100W LED FLOOD LIGHT, 4FT LED FLUORESCENT TUBE…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
52 | EBOCHA | LAR-MCTE-056-2025 | 2025-02-18 | 2025 | FOR THE MAINTENANCE OF THE INTERNAL/EXTERNAL SECURITY LIGHTS | 200 LED FLOOD LIGHT, 300W LED FLOOD LIGHT, 3FT 48 CONTACTOR…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
53 | OBOB | LAR-MCTE-057-2025 | 2025-02-18 | 2025 | FOR THE MAINTENANCE OF THE INTERNAL/EXTERNAL SECURITY LIGHTS IN NEW BASE | 201 LED FLOOD LIGHT, 300W LED FLOOD LIGHT, 3FT 48 CONTACTOR…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
54 | IDU | LAR-MCTE-058-2025 | 2025-02-18 | 2025 | FOR THE MAINTENANCE OF THE INTERNAL/EXTERNAL SECURITY LIGHTS IN IDU F/S | 200W LED FLOOD LIGHT, 300W LED FLOOD LIGHT, 4FT LED FLUORESCENT TUBE…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
55 | OBOB | LAR-MCTE-059-2025 | 2025-02-18 | 2025 | FOR THE MAINTENANCE OF THE INTERNAL/EXTERNAL SECURITY LIGHTS IN GAS PLANT | 200W LED FLOOD LIGHT, 300W LED FLOOD LIGHT, 3FT 48 CONTACTOR..…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
56 | OBOB | LAR-MCTE-060-2025 | 2025-02-22 | 2025 | TO REPLACE PASSING VALVES OF THE INDETIFIED HYDRANTS | 2-1/2 INCHES FNPT BRASS FULL PORT BALL VALVE 600 CLASS | MECHANICAL |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR | [7 empty] | 530.74
57 | OBOB | LAR-MCTE-061-2025 | 2025-02-22 | 2025 | OUT OF STOCK | V-BELT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
58 | OBOB | LAR-MCTE-062-2025 | 2025-02-22 | 2025 | OUT OF STOCK | V-BELT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
59 | OBOB | LAR-MCTE-063-2025 | 2025-02-22 | 2025 | OUT OF STOCK | V-BELT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
60 | AKRI | LAR-MCTE-064-2025 | 23-02-25 | 2025 | FABRICATION OF SPOOL TO TIE-IN THE TEST SEPARATOR OIL OUTLET TO THE LOW PRESSURE SEPARATOR INLET | WELD NECK FLANGE, 4''X900#RJT, BLIND FLANGE, 4''X900# RJT….ETC | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
61 | OBOB | LAR-MCTE-065-2025 | 2025-02-22 | 2025 | OUT OF STOCK | V-BELT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
62 | OBOB | LAR-MCTE-066-2025 | 2025-02-27 | 2025 | MATERIALS FOR REPLACEMENT OF ALL DEAD BATTERIES IN ALL STATIONS | BATTERIES FOR EOC FIRE PUMP -2A, BATTERIES FOR EOC FIRE BUMP -2B…ETC | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
63 | EBOCHA | LAR-MCTE-067-2025 | 2025-02-28 | 2025 | OUT OF STOCK | IGNATION EXCITER | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
64 | OBOB | LAR-MCTE-068-2025 | 2025-03-01 | 2025 | TO REPLACE THE DEAD BATTERY ON GENERATOR GEN 2 AT OBIAFU 43/44 LOCATION PERKINS, 33 KVA RUNNING HR | BATTERY 12V | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
65 | OBOB | LAR-MCTE-069-2025 | 2025-03-03 | 2025 | STOCK NEED REPLENISHMENT | RESIDUAL CURRENT DEVICE DELTA D2-L | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
66 | OBOB | LAR-MCTE-070-2025 | 2025-02-26 | 2025 | TO REPLACE FAN BELT AT THE UNIT 1800 AND 2800 FAN COOL AT OBOB | FAN BELTS | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
67 | IRRI | LAR-MCTE-071-2025 | 2025-02-24 | 2025 | MATERIALS FOR THE REPAIRS OF PERONI PLUNGER PUMP FOR IRRI F/S | PACKING GLANDS-FRONT SIDE, PACKING GLANDS- BACK SIDE | MECHNICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR | [7 empty] | 2029.36
68 | AKRI | LAR-MCTE-072-2025 | 2025-02-28 | 2025 | MATERIALS FOR THE SHUT DOWN VALVE MAINTENANCE JOBS AT AKRI FLOW STATION | KLINGER GASKETS | MECHNICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
69 | OBOB | LAR-MCTE-074-2025 | 2025-03-10 | 2025 | SILENCERS PANEL AND EXPANSION JOINT BROKEN CAUSING VERY HIGH NOISE (UNSAFE CONDITION) | SILENCER PANEL, EXPANSION JOINT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
70 | OBOB | LAR-MCTE-075-2025 | 2025-03-10 | 2025 | SILENCERS PANEL AND EXPANSION JOINT BROKEN CAUSING VERY HIGH NOISE (UNSAFE CONDITION) | SILENCER PANEL, EXPANSION JOINT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
71 | OBOB | LAR-MCTE-077-2025 | 2025-03-10 | 2025 | SILENCERS PANEL AND EXPANSION JOINT BROKEN CAUSING VERY HIGH NOISE (UNSAFE CONDITION) | SILENCER PANEL, EXPANSION JOINT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
72 | OSHIE | LAR-MCTE-076-2025 | 2025-04-09 |  | NEWLY INSTALLED RESIDENTIAL CARAVANS NEED S TO BE POWERED | ARMORED CABLES, 4POLES CIRCUIT BREAKER…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
73 | OBOB | LAR-MCTE-078-2025 | 2025-03-10 | 2025 | SILENCERS PANEL AND EXPANSION JOINT BROKEN CAUSING VERY HIGH NOISE (UNSAFE CONDITION) | SILENCER PANEL, EXPANSION JOINT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
74 | OBOB | LAR-MCTE-079-2025 | 2025-03-10 | 2025 | SILENCERS PANEL AND EXPANSION JOINT BROKEN CAUSING VERY HIGH NOISE (UNSAFE CONDITION) | SILENCER PANEL, EXPANSION JOINT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
75 | KWALE | LAR-MCTE-080-2025 | 2025-03-12 | 2025 | FOR FIXING THE CAT ENGINE OF 6100C | GOVERNOR FOR G399 ENGINE, ACTUATOR | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
76 | OBOB | LAR-MCTE-081-2025 | 2025-03-12 | 2025 | FOR REPLACEMENT OF CLOGGED ELEMENT FILTERS OF TURBO GENERATORS AT IFS | ELEMENT FILTERS | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
77 | OBOB | LAR-MCTE-082-2025 | 2025-03-12 | 2025 | FOR REPLACEMENT OF CLOGGED ELEMENT FILTERS ON TP1 2&3 AT EOC | ELEMENT FILTERS | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
78 | KWALE | LAR-MCTE-083-2025 | 2025-03-08 | 2025 | FOR EXTENSION OF EXHAUST PIPE AND CONSTRUCTION OF THE DIESEL PIPE ON 1000KVA CUMMIS GENERATOR AT UNIT 6400 | STEEL PIPE: 8" X SCH 60 X 12 METERS, ELBOW: 8" X90 X SCH 60….ETC | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
79 | OBOB | LAR-MCTE-084-2025 | 2025-03-15 | 2025 | TO REPLACE THE DEFECTIVE SAPRE PARTS AT UNIT 1800 CG 01A & 01B OB/OB G/P | R22 FREON GAS, THERMISTOR/SENSOR | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
80 | OBOB | LAR-MCTE-085-2025 | 2025-03-15 | 2025 | THE SPARE PARTS/MATERIALS AS PER SPECIFICATIONS FOR COMPLETION OF MAINTENANCE WORK ACTIVITY | EXPANSION VALVE FOR MULTIPLE COMPRESSOR, EXPANSION VALVE MOTOR, SOLENIOD VALVE MOTOR….ETC | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
81 | OBOB | LAR-MCTE-086-2025 | 2025-03-18 | 2025 | REQUIRED TO GREASE THE VALVES(12" X 600RF) ON KICKER LINE TO GTS | CLIMAX PLUG VALVE LUBRICANT, 80 DXK GREASE | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
82 | KWALE | LAR-MCTE-087-2025 | 2025-03-23 | 2025 | TO CHANGE THE DEFECTIVE AND OBSELETE ELECTRICAL DISTRIBUTION BOARD IN THE KITCHEN AT UTILITY BLOCK BULDING RESIDENT AREA | 32A, 10KA, 3P, ACTI9 IC6ON DISBO, MCB….ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
83 | KWALE | LAR-MCTE-088-2025 | 2025-03-19 | 2025 | TO REPLACE FAULTY PARTS OF 420FY-101 A/B FUEL GAS HEATERS | IGNATION TRANSFORMER, ITT BARTON RECORDER, CHART DRIVE, TEMPERATURE | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
84 | KWALE | LAR-MCTE-089-2025 | 2025-03-19 | 2025 | PARTS REQUIRED O REPAIR CHEMICAL INJECTION(TEXTSTEAM) PUMP, SERIES 5000 IN THE PLANT | CHEMICAL INJECTION PUMP(TEXSTEAM PUMP), PILOT VALVE ASSEMBLY, FLIPPER, PIN FLIPPER ARM ASSEMBLY | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
85 | OSHIE | LAR-MCTE-090-2025 | 2025-03-27 | 2025 | MATERIALS NEEDED TO COMPLETE THE MAINTENANCE WORKORDER ACTIVITY AT THE OSHIE TP 1 | MEACH. SEAL | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
86 | SAMABRI | LAR-MCTE-091-2025 | 2025-03-28 | 2025 | TO REPLACE DEAD BATTERY | BATTERY 12V, 100AH | INSTRUMENT |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
87 | OBOB | LAR-MCTE-092-2025 | 2025-03-30 | 2025 | MAINTENANCE OF POWER CABLE ON UNIT 1300-MP-01A E-MOTOR | SCTOCHCASH RESIN KIT (90A-05 SERIES), 50MMSQ STRAIGHT CONNECTOR9FERRULE), 50MMSQ ARMOURED CABLE…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
88 | IRRI | LAR-MCTE-093-2025 | 2025-03-30 | 2025 | TO REPLACE BAD CONDENSATE DRAIN ON ELECTRICAL AIR COMPRESSOR | AUTOMATIC CONDENSATE DRAIN | INSTRUMENT |  | MATERIALS SUPPLIED | EMEKA OKAFOR
89 | KWALE | LAR-MCTE-094-2025 | 2025-04-01 | 2025 | STOCK REPLACEMENT | LUBE OIL PUMP | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
90 | EBOCHA | LAR-MCTE-095-2025 | 2025-03-31 | 2025 | TO REPLACE MECHANICAL SEAL FOR THE TANK PUMP AT THE EOC | MECHANICAL SEAL, MEACH. SEAL REPAIR-KIT | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
91 | OBOB | LAR-MCTE-096-2025 | 2025-04-07 | 2025 | MATERIALS REQUIRED FOR THE PREPARATION OF SHUTDOWN ACTIVITIES AT IDU F/S SAMABIRI | KLINGERSIL C3424 GASKET (8 X 4 X 3MM THICK), ACETYLENE GAS, OXYGEN GAS…ETC | MECHANICAL |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
92 | OBOB | LAR-MCTE-097-2025 | 2025-04-09 | 2025 | NO SUMO PUMP TO INSTALL IN 5 NOS WATER WELLS IN OBOB GAS PLANT | 18.5KW/25HP, 380 SUBMERSIBLE PUMP | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
93 | OBOB | LAR-MCTE-098-2025 | 2025-04-09 | 2025 | THE MATERIALS ARE NEEDED TO COMPLETE THE MAINTENANCE W/O ACTIVITY ON UNIT 810-D1-AIR DRYER | DANFOSS CAPACITY, DANFOSS SOLONIOD VALVE COMPLETE, DANFOSS FILTER DRYER SHORT,…ETC | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
94 | EBOCHA | LAR-MCTE-099-2025 | 2025-04-09 | 2025 | CONTROL ROOM AND SWITCHGEAR 360/960 ARE DARK AND REQUIRED TO IMPROVE THE ILUMINATION | 36W, 2X2FT FLUSHED CEILING MOUNTED LED PANEL LIGHT | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
95 | IDU | LAR-MCTE-100-2025 | 2025-04-12 | 2025 | IDU F/S BACKUP BATTERIES ARE NO MORE RELIABLE AND REQUIRES CHANGING | ALKALINE BATTERIES | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
96 | OBOB | LAR-MCTE-101-2025 | 2025-04-13 | 2025 | MATERIALS NEEDED TO ENSURE AVAILABILITY OF NEW BASE BLOCK D AND EX-ABB CAMP GENERATORS | 200A/HR LEAD ACID BATTERIES AND 12V/24/36/48V BATTERIES | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
97 | OBOB | LAR-MCTE-102-2025 | 2025-04-13 | 2025 | FOR PREPARATION OF SHUTDOWN ACTIVITIES AT IDU F/S AND SAMABIRI | WELDING TONG 600A PURE COPPER | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
98 | OBOB | LAR-MCTE-103-2025 | 2025-04-12 | 2025 | TO REPLACE DEAD BATTERY OF EMERGENCY GENERATOR 1 IN OBIAFU 43/44 LOCATION | 12V, 88AH DRY CALL BATTERY | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
99 | OBOB | LAR-MCTE-104-2025 | 2025-04-14 | 2025 |  | OTE 32 OIL IN DRUM | MECHANICAL |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
100 | EBOCHA | LAR-MCTE-105-2025 | 2025-04-15 | 2025 | TO REPAIR VANDALIZED TR 5 ARMOURED CABLE AT OKWUOWIRIWA | 11KV, 3X95SQMM, XPLE ARMOURED CABLE, 11KV 3CORE COLD SHRINK, SLIM SPLICE KIT WITH FLAME RETAEDANT, 95SQMM | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
101 | KWALE | LAR-MCTE-106-2025 | 2025-04-16 | 2025 | TO REPLACE DEAD 12V, 100AH TUOMO GENERATION BATTERY | SOLITE 12V 100AH BATTERY(KOREA) | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
102 | EBOCHA | LAR-MCTE-107-2025 | 2025-04-17 | 2025 | NO SPARES TO REPLACE THE MALFUNCTIONED COMPONENTS ON TP-2 AT EOC | VALVE SOLENIOD, HMI SCEEN, REGULATOR, PRESSURE…ETC | MECHANICAL |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
103 | OBOB | LAR-MCTE-108-2025 | 2025-04-17 | 2025 | FOR USE IN OBOB GAS PLANT | OTE 46 LUBE OIL | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
104 | OBOB | LAR-MCTE-109-2025 | 2025-04-17 | 2025 | TO FIX NITROGEN GENERATOR UNIT | DIFFERENTTIAL PRESSURE SWITCH, PRESSURE TRANSMITTER, DEW POINT ANALYZER…ETC | MECHANICAL |  | QUOTATION PENDING APPROVAL | AMEZHINIM ODOYI
105 | IDU | LAR-MCTE-110-2025 | 2025-04-17 | 2025 | NO SPARES TO REPLACE THE MALFUNCTIONED COMPONENTS ON TG-B | SWITCH DIFFERENTIAL PRESSURE, BLEED VALVE | MECHANICAL |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
106 | AKRI | LAR-MCTE-111-2025 | 2025-04-17 | 2025 | INSTRUMENTS AND PARTS NEEDED TO REACTIVATE AKRI F/S TEST SEPARATOR | PNEUMATIC LEVEL TRANSMITTER, TEMPERATURE GUAGE…ETC | INSTRUMENT |  | AWAITING UPDATE QUOTATION | AMEZHINIM ODOYI
107 | OBOB | LAR-MCTE-112-2025 | 2025-04-21 | 2025 | TO POWER 5NOS OF NEWLY INSTALLED 5HP AIR CONDITIONERS IN OBOB CONTROL ROOM | 32A, 4P, 400V DIFFERENT CIRCUIT, 4X10 MMSQ FLEXIBLE CABLE, 25MM MALE BUSHING…ETC | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | EMEKA OKAFOR
108 | OBOB | LAR-MCTE-113-2025 | 2025-04-21 | 2025 | VALVE REQUIRED TO REPLACE FAILED VALVES AT RUMUJI PIG LUNCH KICKER LINE ISOLATION | BALL VALVE, GLOBAL VALVE | MECHANICAL |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
109 | IDU | LAR-MCTE-114-2025 | 2025-04-19 | 2025 | TO REPLACE FAULTY I/P ON PCV | ELECTRO-PNEUMATIC POSITIONER | ELECTRICAL |  | AWAITING QUOTATION | AMEZHINIM ODOYI
110 | SAMABRI | LAR-MCTE-115-2025 | 2025-04-19 | 2025 | TO SERVICE/REPAIR LEAKING RADIATOR OF 13.5 KVA PERKINS GENARATOR | RADIATOR | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
111 | EBOCHA | LAR-MCTE-116-2025 | 2025-04-22 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT EBOCHA BOOSTER PUMPS | MECHANICAL SEAL REPAIRING KIT, MECHANICAL SEAL KITS | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
112 | IDU FS | LAR-MCTE-117-2025 | 2025-04-23 | 2025 | ITEM NOT AVAILABLE | GAS FUEL ACTUATOR FOR IDU LP-B | MECHANICAL |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
113 | OBOB | LAR-MCTE-118-2025 | 2025-04-22 | 2025 | STOCK NEED REPLENISHMENT | V-BELT, V-BELT PULLY | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
114 | OBOB | LAR-MCTE-119-2025 | 2025-04-23 | 2025 | TO COMPLETE MAINTENANCE WORK AT OBOB STATIONARY AIR COMPRESSOR | REWINDING OF FAN MOTOR | ELECTRICAL |  | AWAITING UPDATE FROM IYEH | Ikechukwu Iyeh
115 | IRRI FS | LAR-MCTE-120-2025 | 2025-04-24 | 2025 | TO SERVICE IRRI FLOWSTATION CAT 3508B GENERATOR | OIL FILTERS, AIR FILTERS, OIL | MECHANICAL |  | AWAITING UPDATE FROM EMEKA | EMEKA OKAFOR
116 | OSHIE | LAR-MCTE-121-2025 | 2025-05-03 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEM IN OSHIE | C02 GAS CYLINDERS, IG55 GAS CYLINDER, CONTORL PANEL, BREAK GLASS, SMOKE DETECTOR…ETC | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
117 | KWALE | LAR-MCTE-122-2025 | 2025-05-03 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEM IN KWALE | C02 GAS CYLINDERS, IG55 GAS CYLINDER, CONTORL PANEL, BREAK GLASS, SMOKE DETECTOR…ETC | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
118 | AKRI | LAR-MCTE-123-2025 | 2025-05-04 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEM IN AKRI | C02 GAS CYLINDERS, IG55 GAS CYLINDER, CONTORL PANEL, BREAK GLASS, SMOKE DETECTOR…ETC | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
119 | SAMABRI | LAR-MCTE-124-2025 | 2025-05-04 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEM IN SAMABIRI | C02 GAS CYLINDERS, IG55 GAS CYLINDER, CONTORL PANEL, BREAK GLASS, SMOKE DETECTOR…ETC | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
120 | IRRI | LAR-MCTE-125-2025 | 2025-05-04 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEM IN IRRI | C02 GAS CYLINDERS, IG55 GAS CYLINDER, CONTORL PANEL, BREAK GLASS, SMOKE DETECTOR…ETC | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
121 | IDU | LAR-MCTE-126-2025 | 2025-05-03 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEM IN IDU | C02 GAS CYLINDERS, IG55 GAS CYLINDER, CONTORL PANEL, BREAK GLASS, SMOKE DETECTOR…ETC | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
122 | EBOCHA | LAR-MCTE-127-2025 | 2025-05-03 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEM IN EBOCHA | C02 GAS CYLINDERS, IG55 GAS CYLINDER, CONTORL PANEL, BREAK GLASS, SMOKE DETECTOR…ETC | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
123 | EBOCHA | LAR-MCTE-128-2025 | 2025-04-25 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT EBOCHA | STAINLESS STRAINER | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
124 | OBOB | LAR-MCTE-129-2025 | 2025-05-03 | 2025 | REVAMPING/RESTORATION OF FIRE SUPPRESSION SYSTEM IN OBOB | C02 GAS CYLINDERS, IG55 GAS CYLINDER, CONTORL PANEL, BREAK GLASS, SMOKE DETECTOR…ETC | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
125 | AKRI | LAR-MCTE-130-2025 | 2025-04-04 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, AIR FILTER AND OTHER SERVICING PARTS | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
126 | SAMABRI | LAR-MCTE-131-2025 | 2025-04-25 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, AIR FILTER AND OTHER SERVICING PARTS | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
127 | OBOB | LAR-MCTE-132-2025 | 2025-04-26 | 2025 | PLANT USE PUMPS | OSO-68 OIL, OSO-100 OIL AND SAE-40 OIL | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
128 | AKRI | LAR-MCTE-133-2025 | 2025-04-04 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT AKRI BOOSTER PUMPS | STAINLESS STEEL MESH STRAINER | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
129 | EBOCHA | LAR-MCTE-134-2025 | 2025-04-27 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT EBOCHA BOOSTER PUMPS | MECHANICAL SEAL, MECHANICAL SEAL RE-KIT | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
130 | OBOB | LAR-MCTE-136-2025 | 2025-05-02 | 2025 | TO REPAIR VANDALIZED PART OF COMM A POWER TRANSIMISSION CABLE | 11KV XLPE ARMOURED CABLE, SCOTCH TAPES, 120SQMM COPPER FURRULE..ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
131 | OBOB | LAR-MCTE-137-2025 | 2025-05-02 | 2025 | TO REPLACE A FAULTY CIRCUIT BREAKER FOR 1600-PA-01B-GAS PLANT | ABB SACE CIRCUIT BREAKER LNA 63 AUX COIL VOLTAGE=230V | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
132 | OBOB | LAR-MCTE-138-2025 | 2025-04-21 | 2025 | LAR TEST SEPARATOR GAS LINE METER CONSUMABLES | DANIEL ORIFICE GREASE, BARTON RECORDER CHART, RED AND BLUE BARTON PEN | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
133 | OBOB | LAR-MCTE-139-2025 | 2025-05-01 | 2025 | TO FIX FAILED AUXILIARY LUBE OIL PUMP OF TP2 AT EOC | SHIELDED BALL BEARING 12.5X32X10MM | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
134 | OBOB | LAR-MCTE-140-2025 | 2025-05-04 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, AIR FILTER AND OTHER SERVICING PARTS | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
135 | SAMABIRI | LAR-MCTE-141-2025 | 2025-05-04 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, AIR FILTER AND OTHER SERVICING PARTS | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
136 | IDU | LAR-MCTE-142-2025 | 2025-05-04 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, AIR FILTER, AIR FILTER SET(INNER/OUTER) AND RADIATOR COOLANT | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
137 | OSHIE | LAR-MCTE-143-2025 | 2025-05-04 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, FUEL FILTER ELEMENT, WATER SEPARATOR EELMENT, AIR FILTER RADIATOR COOLANT | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
138 | IRRI | LAR-MCTE-144-2025 | 2025-05-04 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, AIR FILTER, AIR FILTER SET(INNER/OUTER) AND RADIATOR COOLANT | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
139 | OBOB | LAR-MCTE-145-2025 | 2025-05-04 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, FUEL FILTER ELEMENT, WATER SEPARATOR EELMENT, AIR FILTER RADIATOR COOLANT | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
140 | KWALE | LAR-MCTE-146-2025 | 2025-05-04 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, AIR FILTER, AIR FILTER SET(INNER/OUTER) AND RADIATOR COOLANT | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
141 | EBOCHA | LAR-MCTE-147-2025 | 2025-05-04 | 2025 | TO CARRY OUT ENIGINE PREVENTIVE MAINTENANCE AND PLANNED MAINTENANCE | LUBE OIL FILTER ELEMENT, AIR FILTER, AIR FILTER SET(INNER/OUTER) AND RADIATOR COOLANT | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
142 | OBOB | LAR-MCTE-148-2025 | 2025-05-04 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT OBOB JFP E-MOTOR REPAIR | BEARING COVER, BEARING, TERMINAL CONNECTOR, COOLING FAN, RETAINER CIRCLIP AND BEARING SHIM | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
143 | AKRI | LAR-MCTE-149-2025 | 2025-05-04 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT AKRI BOOSTER PUMPS | BEARINGS | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
144 | OBOB | LAR-MCTE-150-2025 | 2025-05-08 | 2025 | TO REPLACE ALL FAULTY DB IN BLOCK A,B,C,D AND E IN NEW BASE RESIDENTIAL AREA | D4 DISTRIBUTION BOARD, 3 PHASE, INCLUDING ALL STARSBLOCKS CIRCUIT BREAKERS, D8 DISTRIBUTION BOARD, 3 PHASE, INCLUDING ALL STARBLOCKS CIRCUIT BREAKERS | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
145 | OBOB | LAR-MCTE-151-2025 | 2025-05-09 | 2025 | REPLACEEMENT OF ISOLATION VALVE(OGBAINBIRIR CROSS OVER LOOP TO EBOCHA GAS OUTLET) | GLOBE VALVE SIZE 6" 600 RTJ(FLANGED TYPE) | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
146 | OBOB | LAR-MCTE-152-2025 | 2025-05-09 | 2025 | REPALCEMENT OF ISOLATION VALVE (OGBANBIRI CROSS OVER LOOP TO EBOCHA GAS OUTLET) | GLOBE VALVE SIZE 6" 900 RTJ(FLANGED TYPE) | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
147 | OBOB | LAR-MCTE-153-2025 | 2025-05-10 | 2025 | TO PRESSURE TEST VALVES FOR IDU/SAMABIRI SHUTDOWN ACTIVITIES | 6'' X300#RF BLIND FLANGE, 4''X160#RF BLIND FLANGE, 3''X600#RF BLIND FLANGE, 2''X600#RF BLIND FLANGE | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
148 | OBOB | LAR-MCTE-154-2025 | 2025-05-11 | 2025 | TO REPLACE FAULTY LEVEL TRANSMITTER | LEVEL TRANSMITTER | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
149 | EBOCHA | LAR-MCTE-155-2025 | 2025-05-07 | 2025 | TO REPLACE A FAULTY EARTH LEAKAGE RELAY FOR TANK PUMP | EARTH LEAKAGE RELAY, AUX=13=230V. 23=115VDC/AC, RELAY AUX=240VD(CONTANT)=10/250V | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
150 | OBOB | LAR-MCTE-156-2025 | 2025-05-12 | 2025 | TO REPLACE ALL FAULTY SUMO PUMP CABLES FOR 1820/820 - GAS PLANT | 4cX10sqmm, 600V COPPER HEAVY DUTY THW/PVC FLAT SUMO PUMP CABLE | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
151 | OBOB | LAR-MCTE-157-2025 | 2025-05-24 | 2025 | DELTA MATERIALS FOR MAJOR INSPECTION(DUE TO COMPRESSOR HIGH VIBRATION) | LABYRINTH RINGS, RADIAL BEARING, GASKETS AND RTD PT100 | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
152 | OBOB | LAR-MCTE-158-2025 | 2025-05-24 | 2025 | CRITICAL SPARE PARTS | ANALOG AMP., DIGITAL IN/OUT, VIB CONDITIONING CARD, ANALOG I/O MOD…ETC | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
153 | KWALE | LAR-MCTE-159-2025 | 2025-05-13 | 2025 | TO REPLACE THE BAD ONES IN THE UNIT | AC-DC POWER SUPPLY INPUT AC230V/120V 60/50Hz 3.2/5/5A OUTPUT DC- 24V/10A | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
154 | OBOB | LAR-MCTE-160-2025 | 2025-05-17 | 2025 | FOR 1640A FLUSHING AND RECHARGING -QTY- 45 DRUMS STOCK REPLENISHMENT -35 DRUMS | LUBE OIL | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
155 | OBOB | LAR-MCTE-161-2025 | 2025-05-16 | 2025 | INSATLLATION OF TURBINE IN 1620 B -MS1002D PGT5 | TURBINE SPARE PARTS | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
156 | OBOB | LAR-MCTE-162-2025 | 2025-05-18 | 2025 | STOCK REPLENISMENT | COMPLETE INTERFACE MODULE, MARK IV CARD, ELECTRONIC CARD VIDEO…ETC | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
157 | OBOB | LAR-MCTE-163-2025 | 2025-05-21 | 2025 | FOR INTERVENTION JOBS | PORTABLE WELDING MACHINE, BIG BLUE MILLER WELDING MACHINE, WELDING CABLES, EXTENSION CABLES….ETC | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
158 | OBOB | LAR-MCE-164-2025 | 2025-05-19 | 2025 | TO CHECK AND RECTIFY FAULTY UNIT 4250 SDV-001 | 3 WAYS SOLENIOD VALVE | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
159 | OBOB | LAR-MCTE-165-2025 | 2025-05-19 | 2025 | TO CHECK AND RECTIFY FAULTY TEMPERATURE TRANSMITTER AT UNIT 4250-TT002 | FLOW TRANSMITTER | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
160 | OBOB | LAR-MCTE-166-2025 | 2025-05-19 | 2025 | TO CHECK AND RECTIFY FAULTY TEMPERATURE TRANSMITTER AT UNIT 4250-LT-003 | FLOW TRANSMITTER | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
161 | OBOB | LAR-MCTE-167-2025 | 2025-05-26 | 2025 | TO BE USED AT UNIT 540,2540,1300, SWITCHGEAR ROOMS, 1420 MOV AND FLOOD TOWER LIGHTINGS | THERMAL OVERLOAD(25-40A), CIRCUIT BREAKERS …ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
162 | OBOB | LAR-MCTE-168-2025 | 2025-05-29 | 2025 | THE MATERIALS ARE NEEDED TO COMPLETE THE MAINTENANCE W/O ACTIVITY ON UNIT 1800-GA-01A | PILLOW BEARING, OVERLOAD RELAY | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
163 | OBOB | LAR-MCTE-169-2025 | 2025-05-26 | 2025 | NEW 11KW E.MOTOR FOR 1600-PA-05 PUMP | ELECTRIC MOTOR | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
164 | OBOB | LAR-MCTE-170-2025 | 2025-05-31 | 2025 | TO REPLACE VANDALIZED CABLE AND MATERIALS AT OBF 43/44 HELIPAD | 4X16SQMM ARMOURED CABLE, 4X4SQMM ARMOURED CABLE, 4 POLES, 63A MCB 2 POLES, 10A MCB | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
165 | OBOB | LAR-MCTE-171-2025 | 2025-05-30 | 2025 | ZERO STOCK NEED FOR REPLENISHMENT | BEARINGS | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
166 | OBOB | LAR-MCTE-172-2025 | 2025-05-31 | 2025 | TO REPLACE EXTERNAL AND INTERNAL LIGHTING IN OBOB G/P | 100W, IP65, 230V LED FLOOD LIGHT, 200W IP65 230 LED FLOOD LIGHT, 400W CHOKE, 400W, MERCURY VAPOUR LAMPS….ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
167 | OBOB | LAR-MCTE-174-2025 | 2025-06-02 | 2025 | FOR FLUSHING AND STOCK REPLACEMENT | LUBE OIL FILTER | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
168 | OBOB | LAR-MCTE-175-2025 | 2025-06-01 | 2025 | LUBE OIL FLUSH ON THE CIRCUIT | LUBE OIL | ROTATING EQUIP |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
169 | EBOCHA | LAR-MCTE-176-2025 | 2025-05-04 | 2025 | TO PREPARE ALKALINE BATTERIES FOR NEW BASE EDG | POATSIUM HYDROXIDE(KOH) MIXED ELECTROLYE, ALKALINE HYDROMETER | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
170 | EBOCHA | LAR-MCTE-177-2025 | 2025-05-04 | 2025 | TO REPAIR FAILED POWER CABLE TO BLOCKS A/B STEP DOWN TRANSFORMER | 11KV, 3X120SQMM CABLE SPLICING KIT, 3M COLD SHRINK, SCOTCH TAPE 33 AND 23…ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
171 | OBOB | LAR-MCTE-178-2025 | 2025-07-04 | 2025 | HELLIUM CYLINDER ARE REQUIRED FOR SALE GAS FLOW METERING CORRECTION | HELLIUM CYLINDER, GRADE -N5, PRUITY -99.999%, FILL PRESSURE -3000PSI,CYLINDER VALVE CONNECTION -BS3, CYLINDER CAPACITY -50LTS | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
172 | OBOB | LAR-MCTE-179-2025 | 2025-06-05 | 2025 | URGENTLY NEEDED FOR FLOW LINE WELDING ACTIVITIES | OXYGEN GAS IN CYLINDER 75M3, ACETYLENE GAS IN CYLINDER 6.5M3 | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
173 | EBOCHA | LAR-MCTE-180-2025 | 2025-06-05 | 2025 | TO CARRY OUT CORRECTIVE MAINTENANCE WORK ORDER JOB ON EOC BOOSTER PUMP6 | MEACHANICAL SEAL, SEAL SIZE 48MM | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
174 | AKRI | LAR-MCTE-181-2025 | 2025-06-05 | 2025 | TO CARRY OUT CORRECTIVE MAINTENANCE WORK ORDER JOB ON THE UNIT | MEACHANICAL SEAL, SEAL SIZE 50MM | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
175 | OBOB | LAR-MCTE-182-2025 | 2025-06-05 | 2025 | TO RECTIFY METHANOL INJECTOR | 3/4'' STAINLESS STEEL TUBING PIPE | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
176 | OSHIE | LAR-MCTE-183-2025 | 2025-06-06 | 2025 | REPLACEMENT OF PACKAGING GLAND FOR FIRE PUMP 1&2 TO ELIMINATE PACKING GLAND LEAKAGE | GRAPHITE PACKING GLAND | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
177 | OBOB | LAR-MCTE-186-2025 | 2025-06-09 | 2025 | LOW STOCK/NEED RESTOCKING | AIR BAG / CYLINDRICAL AIR AND CONICAL AIR FILTERS CATRIDGE | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
178 | OBOB | LAR-MCTE-187-2025 | 2025-04-20 | 2025 | RAPLACEMENT OF BATTERY FOR 1820 FIRE PUMP 3. | COUPLING | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
179 | OBOB | LAR-MCTE-188-2025 | 2025-06-19 | 2025 | MAINTENANCE OF 720 EFFULENT PUMP AT OBOB | PUMP SHAFT, SHAFT SLEEVE OIL BATH, BEARING HOUSING RETAINER SLEEVE | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
180 | OBOB | LAR-MCTE-189-2025 | 2025-06-22 | 2025 | MECHANICAL SEAL | MECHANICAL SEAL(SIZE) 59.50CM | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
181 | KWALE | LAR-MCTE-190-2025 | 2025-06-14 | 2025 | TO REPAIR FAULTY TUOMO FG WILSON P65-5 GENERATOR | AVR (FG WILSON P65-5 GENERATOR), FUEL PUMP (FG WILSON P65-5 GENERATOR) OIL FILTER, FUEL FILTER, AIR FILTER | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
182 | EBOCHA | LAR-MCTE-191-2025 | 2025-06-14 | 2025 | TO REPAIR VANDALIZED TR5 11KV UNDERGROUND TRANSMISSION ARMOURED CABLE ALONG OKWUOWIRIWA AXIS | 11KV 3X 120 SQMM, XPLE ARMOURED CABLE, 11KV, 3CORE, COLD SHRINK, SLIM SPLICE KIT WITH FLAME RETARDANT, ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
183 | KWALE | LAR-MCTE-192-2025 | 2025-06-17 | 2025 | TO RECTIFY FREQUENT STARTING FAILURE | AUXILIARY CONTACTOR 10A/240V AC, CONTACTOR(IEC 60947, VDE 0660) 10A/600V AC | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
184 | OBOB | LAR-MCTE-193-2025 | 2025-06-22 | 2025 | REKIT OF MECHANICAL SEAL AND COMPLETE MECHANICAL SEAL | REKIT OF MECHANICAL SEAL, COMPLETE MECHANICAL SEAL | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
185 | OBOB | LAR-MCTE-194-2025 | 2025-06-23 | 2025 | TO PROVIDE POWER SUPPLY TO NEWLY INSTALLED AIR CONDITIONED IN EBOCHA OIL CENTER CONTROL ROOM/NEW SWICT GEAR ROOM | 5X6sqmm FLEXIBLE CABLE, 16A 4POLE,3PHASE DIFFERENTIAL CIRCUIT BREAKER, I INCH SCREW NAIL….ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
186 | AKRI | LAR-MCTE-195-2025 | 2025-04-19 | 2025 | TO REPLACE FAULTY INNER MECHANISM, TEMPERATURE AND PRESSURE GAUGES | INNER MECHANISM, TEMPERATURE GAUGES, PRESSURE GAUGES | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
187 | IRRI | LAR-MCTE-196-2025 | 2025-06-30 | 2025 | TO SERVICE IRRI FLOWSTATION CAT 3508A THAT WAS DUE FOR SERVICING | OIL, AIR FILTERS | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR | [5 empty] | Approved Quotation\2025\LAR 2025 A-Q\ |  |  | N3,928,827.87
188 | EBOCHA | LAR-MCTE-197-2025 | 2025-06-26 | 2025 | TO REPAIR VANDALIZED TR 5 ARMOURED CABLE AT OKWUOWIRIWA | 11KV, 3X95SQMM, XPLE ARMOURED CABLE, 11KVA 3CORE, COLD SHRINK, SLIM SPLICE KIT WITH FLAME RETARDANT, 95SQMM CABLE LUG ….ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
189 | OBOB | LAR-MCTE-198-2025 | 2025-06-26 | 2025 | TO POWER 4NOS INSTALLED CARAVANS AT OBF 43/44 LIFE CAMP | 4X50SQMM, 600/1000V ARMOURED CABLE, 4X10SQMM, 600/1000V ARMOURED CABLE….ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
190 | OBOB | LAR-MCTE-199-2025 | 2025-06-28 | 2025 | DIVERSION OF OILY WATER TO TANK PUMP SUCTION AT EOC | CARBON STEEL PIPE 2'' SCH 80 WALL THK 5.64MM, EQUAL TEE 3'' SCH 40 WALL THK 5.49 mm…ETC | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
191 | KWALE | LAR-MCTE-200-2025 | 2025-06-18 | 2025 | TO RESTORE A TILTING TANK STAND AT TUOMO | WELDING ELECTRODES 7018 X 3.25mm, WELDING ELECTRODES 6010 X 3.25mm, GALVANIZED GRATINGS 900 X 600 mm…etc | CONSUMABLES |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
192 | OSHIE | LAR-MCTE-201-2025 | 2025-06-29 | 2025 | THE CLINIC LIGHTS ARE DEAD AND REQUIRES URGENT ATTENTION | 24, IFT BY 1 FT POP FLUSHED LED LIGHT, E27 CERAMIC LAMP HOLDER, 230V 18W, E27, LED LAMP, 230V, 100W LED FLOOD LIGHT , 1P65 | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
193 | OBOB | LAR-MCTE-202-2025 | 2025-06-30 | 2025 | TO POWER HYDRANT WATER SUMO PUMP AT OBF 43/44 RIG LOCATION | 4X50SQMM, 600/1000V ARMOURED CABLE, 4X10SQMM, 600/1000V ARMOURED CABLE, 3PHASE, 380V, 18KW STARTER PANEL….ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
194 | IRRI | LAR-MCTE-203-2025 | 2025-06-05 | 2025 | TO REPLACE DEFECTIVE CONTROL PANELS IN THE WATER TREATMENT PLANT | CONTROL BOX PANEL: SAER ELETROPOMPE | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
195 | KWALE | LAR-MCTE-204-2025 | 2025-03-13 | 2025 | TO REPLACE THE BAD ONES IN THE UNIT | AC-DC POWER SUPPLY INPUT-AC230V/120V 60/50Hz 3.2/5/5A OUTPUT-DC 24V/10A | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
196 | OBOB | LAR-MCTE-205-2025 | 2025-06-02 | 2025 | REPLACEMENT OF DAMAGED PCV AT 3420 REGEN | PRESSURE(REDUCING) CONTROL VALVE, PCV, PRESS RATING 0.4 BAR TO 15 BAR | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
197 | IRRI | LAR-MCTE-206-2025 | 2025-06-03 | 2025 | REPLACEMENT OF FAULTY PARTS FOR IRRI STATIONARY AND MOBILE AIR COMPRESSOR | AIR FILTER, FUEL FILTER, WATER SEPARATOR, PRIMER PUMP | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
198 | OBOB | LAR-MCTE-207-2025 | 2025-07-03 | 2025 | TO CARRYOUT FUNCTIONAL CHECKS ON UNIT 1820/820 WATER NETWORK SYSTEM RECYCLING CONTROL VALVES | LEVEL CONTROL VALVE, AIR TO OPEN | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
199 | OBOB | LAR-MCTE-208-2025 | 2025-07-03 | 2025 | TO CARRYOUT FUNCTIONAL CHECKS ON UNIT 1820/820 WATER NETWORK SYSTEM RECYCLING CONTROL VALVES | LEVEL CONTROL VALVE, AIR TO OPEN | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
200 | OBOB | LAR-MCTE-209-2025 | 2025-06-07 | 2025 | INSPECTION OF UNITS GENERATORS, ELECTRICAL SYSTEM, AVR AND OTHER RELALTED COMPONENTS THAT MAY PREVENT THE UNIT FROM ACCEPTING SUFFICENT LOAD. | GENERATOR AND AVR FSE | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
201 | KWALE | LAR-MCTE-210-2025 | 2025-03-08 | 2025 | FOR EXTENSION OF EXHAUST PIPE AND CONSTRUCTION OF THE DIESEL PIPE ON 1000KVA CUMMIS GENERATOR AT UNIT 5400 | STEEL PIPE: 8" X SCH 60 X 12 METERS, ELBOW: 8" X90 X SCH 60….ETC | CONSUMABLES |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
202 | KWALE | LAR-MCTE-211-2025 | 2025-04-02 | 2025 | TO REPLACE BAD LUBE OIL PUMP AT UNIT 360B | LUBE OIL PUMP | GMC |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
203 | IRRI | LAR-MCTE-212-2025 | 2025-02-08 | 2025 | NEEDED ELECTRICAL CONSUMABLES AND MATERIALS THAT WILL ENABLE US CARRY OUT PREVENTIVE MAINTENANACE ACTIVITIES IN THE PLANT, RESIDENTIAL AREAS | 13A SOCKET, AND 15A SOCKECT 50/50, 13A PLUG AND 15A PLUG 50/50, 6W LED BULB AND 7W LED BULB 50/50, 15 W LED BULB…ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
204 | OBOB | LAR-MCTE-213-2025 | 2025-06-25 | 2025 | REPLACEMENT OF MECHANICAL TECHNICAL SEAL FOR 1600-PA-07 | MEACHANICAL SEAL | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
205 | OBOB | LAR-MCTE-214-2025 | 2025-07-04 | 2025 | TO REPLENISH STOCK FOR REGENERATION OF UNIT 1600 DEMINIRALIZE WATER AND SYSTEM CHARGE OF UNIT 1670 | SODIUM HYDROXIDE(LIQUID) 33-36%, HYDROCHLORIC ACID 32-35% CONC.(200 DEUMS), ACTIVATED METHYL DIETHANOLAMINE(aMDEA) | CHEMICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
206 | KWALE | LAR-MCTE-215-2025 | 2025-06-16 | 2025 | CONSUMABLES FOR MAINTENANCE WORKS IN AND OUTSIDE THE PLANT | OXYGEN GAS, ACETYLENE GAS, WELDING ELECTRODES 7018 X 3.25MM & 6010 X 3.25 MM, CUTTING DISC 9'' AND GRINDING DISC 7'' | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
207 | OBOB | LAR-MCTE-216-2025 | 2025-07-07 | 2025 | TO CLOSE OUT THE FINDINGS OF THE ACTION PLANS 09/06/2025 | 2FT FLYCATCHER FITTINGS, 56'' CEILING FANS, 2 FT LED FLOURESCENT TUBES AND 24 LED C-TORCH BULBS | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
208 | OBOB | LAR-MCTE-224-2025 | 2025-07-07 | 2025 | REPLACEMENT OF SPECTACLE BLIND FOR UNIT 320 | 10''X600# RJT SPECTACLE BLIND, 10'' X 60# RJT…ETC | MECHANCAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
209 | OBOB | LAR-MCTE-225-2025 | 2025-07-10 | 2025 | TO REPLACE BAD AVR AND TO RESOLVED UNIT LOAD ISSUES | AVR-AISTON MICROTECH DX21 | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
210 | OBOB | LAR-MCTE-226-2025 | 2025-07-10 | 2025 | CARRYOUT SERVICING OF EDG 350KVA GENERATOR NEW BASE | FUEL FILTERS | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR | [5 empty] | Approved Quotation\2025\LAR-MCTE-226 2025 A-Q\ |  |  |  | N141,885.35
211 | OBOB | LAR-MCTE-227-2025 | 2025-07-15 | 2025 | NEED TO RESTOCK | TEMPERATURE SWITCH, SERVO VALVE 5 GPM, GAS SENSORS | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
212 | OBOB | LAR-MCTE-228-2025 | 2025-07-18 | 2025 | ZERO STOCK AND IT'S NEEDED IN THE ACTIVITIES | 3 WAY CERAMICS TERMINAL BLOCKS HIGH TEMP. PORCELAIN CERAMIC CONNECTOR AND 2 WAY CERAMICS TERMINAL BLOCKS | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
213 | OBOB | LAR-MCTE-229-2025 | 2025-07-17 | 2025 | RE-STOCKING | HYDRAULIC HOSE- CH668-24, DN 88 50 BAR/725 | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
214 | OBOB | LAR-MCTE-236-2025 | 2025-07-21 | 2025 | FOR REVAMPING OF OBIAFU 43/44 HELIPAD LIGHT SYSTEM | DOWNING MODEL 1601 LED PERIMETER LIGHT UNIT, GREEN PERIMETER LED, SMALL LED DRIVER UNIT…ETC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
215 | OBOB | LAR-MCTE-237-2025 | 2025-07-23 | 2025 | RESTOCKING FOR CLEANING | CLEAN BLADE 207KG GTC 1000 DEGREASER | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
216 | OBOB | LAR-MCTE-239-2025 | 2025-07-26 | 2025 | TO REPLACE FAULTY AUXILLARY CONTACTOR FOR UNIT 2540-EP 01 | 4 POLES, AUXILLARY CONTACTOR, COIL VOLTAGE 110VDC, ITH=10A, UI=690V, 3NO, INC | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
217 | OBOB | LAR-MCTE-240-2025 | 2025-07-26 | 2025 | TO REPLACE BLOWN OUT 6KV HRC FUSES FOR 1670-PA-02A/C | 6KV HRC FUSES, 1N=160A, UN=7.2KV, 11=45KA, 13=500A, IEC 282-1:1985…LENGTH=58CM | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
218 | OBOB | LAR-MCTE-241-2025 | 2025-07-26 | 2025 | REPLACEMENT OF BATTERY FOR 810-K1E | BATTERY | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
219 | IDU | LAR-MCTE-242-2025 | 2025-07-27 | 2025 | TO REPAIR IDU FIRE PUMP 2B KICK STARTER | REPAIR OF KICK STARTER | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
220 | IDU | LAR-MCTE-243-2025 | 2025-07-28 | 2025 | MATERIALS REQUIRED FOR INSTRUMENTATION JOBS AT IDU VALVES MCTE SD PROJECT | FLEXIBLE HOSE 10MX1/4'', 1/4 STARIGHT CONNECTOR, DEGREASE/SOLVENT, 1/2'' TUBE PIPE CONNECTOR…..ETC | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
221 | SAMABRI | LAR-MCTE-244-2025 | 2025-07-28 | 2025 | MATERIALS REQUIRED FOR INSTRUMENTATION JOBS AT SAMABRI VALVES MCTE SD PROJECT | SOLENIOD VALVE 24VDC & 110VDC, COIL CONTACTOR 230 VAC, 1/2'' TRANSPARENT HOSE…...ETC | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
222 | OBOB | LAR-MCTE-245-2025 | 2025-07-27 | 2025 | MATERIAL REQUEST FOR THE PROVISION OF SPARES FOR USE OF WELL TESTING ACTIVITIES IN EBOCHA OIL CENTRE | 10'' ORIFICE PLATE THICKNESS 1/4 SET(ORID 1.5,325,45), 10'' TEFLON PLATE HOLDER | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
223 | OBOB | LAR-MCTE-246-2025 | 2025-07-26 | 2025 | ZERO STOCK | LUBE OIL FILTER CATRIDGE | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
224 | OBOB | LAR-MCTE-247-2025 | 2025-07-26 | 2025 | ZERO STOCK | DETRONICS COMBUSTIBLE GAS SEBSOR- M20, THERMOCOUPLE WIRE BRAIDED FIBERGLASS INSULATION, LIGUID LEVEL INDICATOR ASS.Y | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
225 | KWALE | LAR-MCTE-248-2025 | 2025-08-04 | 2025 | TO REPLACE THE LEAKING MECHANICAL SEAL OF UNIT 6100 BOOSTER BP702 PUMP | RUHRPUMPEN PUMP, TYPE 4X8X15MSCE, MECHANICAL SEAL ASSEMBLY. | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
226 | OBOB | LAR-MCTE-249-2025 | 2025-08-05 | 2025 | TO REPAIR VANDALIZED TR 5 ARMORED CABLE FROM GAS PLANT TO OKWUOWIRIWA | 11KV, 3CORE, COLD SHRINK, SLIM SPICE KIT WITH FLAME RETARDANT, 120SQMM FERRULES, SCOTCH TAPE 23 | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh | [5 empty] | Approved Quotation\2025\LAR 2025 A-Q\BUDGETARY |  |  |  | 209625
227 | OBOB | LAR-MCTE-250-2025 | 2025-08-05 | 2025 | MATERIALS REQUIRED FOR MAINTENANCE OF CUMMINS ENGINE QSX-15 | CAM SHAFT 0-RING SEAL, GASKET, O-RING SEAL | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
228 | OBOB | LAR-MCTE-251-2025 | 2025-08-03 | 2025 | LEVEL TRANSMITER FOR MAINTENANCE OF 1310-LT-05 UNIT | LEVEL TRANSMITER | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
229 | KWALE | LAR-MCTE-252-2025 | 2025-08-05 | 2025 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT KWALE BOOSTER PUMP 702 | MECHANICAL SEAL RE-KIT | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
230 | KWALE | LAR-MCTE-253-2025 | 2025-08-04 | 2025 | REQUEST FOR OIL MAINTENANCE ACTIVITY/USE AT KWALE GAS PLANT | SIC 150, OTE-32, GEUM 30, SAE 30, OSO100, OSO 68, BLASIA 150 | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
231 | OBOB | LAR-MCTE-254-2025 | 2025-08-07 | 2025 | FOR MODIFICATION OF RESIDENTIAL PORTACABIN STAIRCASES AT OBIAFU | 1''SCH 40 GALVANISED PIPE | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
232 | OBOB | LAR-MCTE-255-2025 | 2025-08-07 | 2025 | FOR FABRICATION OF SPOOL TO SUPPLY FUEL GAS FROM IDU TO EBOCHA | WN FLANGE 2''X 600 RTJ, GLOBE VALVE 2''X 600 RJT, CHECK VALVE 2''X600 RJT …ETC | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
233 | OBOB | LAR-MCTE-257-2025 | 2025-08-07 | 2025 | REPLACEMENT OF FAULTY LEVEL TRANSMITTER | LEVEL TRANSMITER | INSTRUMENT |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
234 | IRRI | LAR-MCTE-259-2024 | 2024-12-27 | 2024 | TO REPLACE THE ALREADY CORRODED CHOKE BOX AT OLEH 3 L IN IRRI | CHOKE BOX 3 1/8 X 5000, RING JOINT RX 35(X AXIS 230MM: Y AXIS 250MM) | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
235 | KWALE | LAR-MCTE-260-2025 | 2025-08-07 | 2025 | TO REPLACE THE CORROEDED CHOKE BOX ON OLEN ils IN IRRI FLOW STATION | WN FLANGE 3, 1/16X10000 SCHEDULE 120, 4'EQUAL TEE SCHEDULE 120, 4' END CAP SHEDULE 120….ETC | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
236 | OBOB | LAR-MCTE-261-2025 | 2025-08-07 | 2025 | REPLACEMENT OF FAULTY I/P TRANSDUCER | I/P TRANSDUCER | ELECTRICAL |  | QUOTATION APPROVAL PENDING | Ikechukwu Iyeh
237 | OBOB | LAR-MCTE-264-2025 | 2025-08-10 | 2025 | GE FR5001 GAS TURBINE MAJOR OUTAGE- KGP | NDT SPECIALIST, TORGUE CONVERTER SPECIALIST, TORGUE CONVERTER SUPPORT TECHNICIAN….ETC | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
238 | OBOB | LAR-MCTE-265-2025 | 2025-08-19 | 2025 | FOR TURBINS TOPING | OTE 32 LUBE OIL, OTE 46 | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
239 | OSHIE | LAR-MCTE-268-2025 | 2025-08-17 | 2025 | REPLACEMENT OF BROKEN COUPLING FOR BOSSTRE PUMP 1 | BOOSTER PUMP 1COUPLING | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR
240 | KWALE | LAR-MCTE-274-2025 | 2025-08-17 | 2025 | OEM INSPECTION AND SERVICE OF 701 BOOSTER PUMP | BOOSTER PUMP | MECHANICAL |  | QUOTATION APPROVAL PENDING | EMEKA OKAFOR