## Sheet1
S/N | LOCATION | MRF NUMBER | REQUEST DATE | YEAR | REASON FOR REQUEST | SERVICE\MATERIAL | DISCIPLINE | STATUS NOTES | CALL OFF NUMBER | REMARKS
1 | OB/OB | LAR-MTCE-260-2024 | 2024-08-25 | 2024 | TO REPLACE THE FAULTY POSITIONER OF UNIT 710-PCV-01B FLARE VALVE | DIGITAL VALVE CONTROLLER (POSITIONER) - FISHER | INSTRUMENT | AWAITING UPDATE FROM DEPUTY MANAGER ROTATING EQUIPMENT. | 10119656 | Emeka Okafor
2 | OB/OB | LAR-MTCE-261-2024 | 2024-08-17 | 2024 | TO CARRY OUT ENGINE PREVENTIVE MAINTENANCE FOR JOCKEY | PARTS FOR PLANNED MAINT OF UNIT 1820 JOCKEY PUMP 1 | INST AIR COMPRESSOR | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
3 | OSHIE F/S | LAR-MTCE-262-2024 | 2024-08-09 | 2024 | ROUTINE MAINT OF GEN No. 1 IN OSHIE FLOWSTATION | NGEO ADVANCE 40 LUBE OIL, OIL FILTER | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
4 | OBOB | LAR-MCTE-263-2024 | 2024-08-27 | 2024 | STOCK REPLENISHMENT | AMMETER, CURRENT TRANSFER | GMC | AWAITING QUOTATION |  | Emeka Okafor
5 | EOC/IDU | LAR-MCTE-264-2024 | 2024-08-25 | 2024 | REPLACEMENT OF MALFUNCTIONED ITEMS FOR TP-1/3 AND TG-B | COMPUTER SYSTEM TT400 MULTI EOC TP-1, PRIMARY SHUT OFF VALVE AND TRIP PNEUMATIC SOLENOID FOR IDU TG-B | TURBINE & ROT EQUIPT | AWAITING QUOTATION |  | Emeka Okafor
6 | OBOB | LAR-MCTE-265-2024 | 2024-08-30 | 2024 | FOR ROUTINE MAINTENANCE | 10'' X 150 RF BLIND FLANGE | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
7 | EBOCHA | LAR-MCTE-266-2024 | 2024-09-01 | 2024 | REPLACEMENT OF BAD CONTROL PANEL/DEAD BATTERIES AND TO CARRY OUT GENERAL SERVICING | BATTERY, CONTROL PANEL AND SERVING PARTS | GMC | AWAITING QUATATION |  | Emeka Okafor
8 | OB/OB | LAR-MTCE-267-2024 | 2024-09-09 | 2024 | FOR UNIT 720 API SKIMMER PUMP CONTROL CASSETTE JOB | SIEMENS CONTACTOR 3TH80 3I-OA COIL 220V; 50/60HZ; 3NO.INC | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
9 | IDU F/S | LAR-MTCE-268-2024 | 2024-09-09 | 2024 | UNIT 220 - TO OPERATE OIL DELIVERY LINE IN AUTO MODE | SOLENOID VALVES; FLOW AND PRESSURE TRANSMITTERS | INSTRUMENT | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
10 | IDU F/S | LAR-MTCE-269-2024 | 2024-09-10 | 2024 | TO REPLACE CORRODED OIL OUTLET SPOOL FOR IDU OLD NAG SEPARATOR | WN FLANGE AND ELBOW 4" | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
11 | IRRI F/S | LAR-MCTE-270-2024 | 2024-09-19 | 2024 | MATERIALS TO PUT EQUIPMENT IN GOOD WORKING CONDITION | WATER PUMP, BATTERIES 12V-120AH, AVR, CAT NGEO ADVANCED 40/331-7301 | GMC | AWAITING QUOTATION |  | Emeka Okafor
12 | IRRI F/S | LAR-MTCE-271-2024 | 2024-09-22 | 2024 | MATERIALS TO RESTORE POWER TO UNIT 470 (G3508A) | CAT NGEO ADVANCED 40/331-7031 LUBE OIL AND WATER PUMP | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
13 | IDU F/S | LAR-MCTE-273-2024 | 2024-09-28 | 2024 | TO CARRY OUT MAINTENANCE OF COMPRESSOR, PROGRAMMING OF ELECTRINIK MODULE | OEM ATLAS CAPCO SERVICE ENGINEER ATTENTION(PROGRAMMING OF ELECTRINIK MODULE) | AIR COMPRESSOR | AWAITING UPDATE FROM DEPUTY MANAGER ROTATING EQUIPMENT. | 10119656 | Emeka Okafor
14 | EOC | LAR-MCTE-274-2024 | 2024-09-28 | 2024 | OEM IS REQUIRED TO CHECK AND RECTIFY THE VSD DISPLAY FAULT AND ANYOTHER FAULT THAT MAY ARISE DURING TROUBLE | OEM ATLAS CAPCO SERVICE ENGINEER ATTENTION(FOR ZT 90 VSD UNKNOWN ERROR DISPLAY) | AIR COMPRESSOR | AWAITING UPDATE FROM DEPUTY MANAGER ROTATING EQUIPMENT. | 10119656 | Emeka Okafor
15 | OBOB | LAR-MCTE-275-2024 | 2024-09-23 | 2024 | TO REVAMP AIR DRYER, MANUROE | COMPRESSOER MTZ 100 SHAVE, SOLENIOD VALVE AND COIL, DRYER 1/2 SHORT…ETC | HVAC | AWAITING UPDATE FROM DEPUTY MANAGER ROTATING EQUIPMENT. | 10119656 | Emeka Okafor
16 | IRRI | LAR-MCTE-276-2024 | 2024-09-23 | 2024 | OEM TO CHECK THE CONTROL MODULE FOR FAULTS AND POSSIBLY REPAIR | OEM ATLAS CAPCO SERVICE ENGINEER ATTENTION( FOR ZT 30 MODULE CHECK, INSPECT AND NECESSARY CORRECTION FOR NOT DISPLAYING PROPERLY | AIR COMPRESSOR | AWAITING UPDATE FROM DEPUTY MANAGER ROTATING EQUIPMENT. | 10119656 | Emeka Okafor
17 | KWALE | LAR-MCTE-277-2024 | 2024-10-03 | 2024 | STOCK REPLACEMENT | HMI: CPU: CM 575 2.0 GHZ, MEMORY;512MB, HDD:320GB | PLANTGERIA | AWAITING UPDATE WILSON |  | Emeka Okafor
18 | OBOB | LAR-MCTE-278-2024 | 2024-10-04 | 2024 | ZERO STOCK - TO REPLENISH | LUBE OIL OTE 32(OR EQUIVALENT) | PLANTGERIA | AWAITING UPDATE WILSON |  | Emeka Okafor
19 | OBOB | LAR-MCTE-279-2024 | 2024-10-06 | 2024 | TR6 11KV UNDERGROUND TRANSMISSION CABLE | X120MMSQ 11KV XPLE CABLE, 3X120MMSQ 11KV STARIGHT THROUGH JOINT KIT, SCOTCH 23 INSULATION TAPE…ETC | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
20 | KWALE | LAR-MCTE-280-2024 | 2024-10-05 | 2024 | TO REPLACE FAULTY UNIT 420 FUEL HEATER IGNITION TRANSFORMER | 420 FY-101A/B FUEL GAS HEATER IGNITION TRANSFORMER | INSTRUMENT MAINTENANCE | AWAITING UPDATE WILSON |  | Emeka Okafor
21 | KWALE | LAR-MCTE-281-2024 | 2024-10-05 | 2024 | REPLACEMENT OF FAILED SEWAGE PUMP | WATER PUMP 7.5KW 10HP, 380V 50HZ 2860 R/MIN 2"X2" IP68 ICL B | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
22 | OBOB | LAR-MCTE-282-2024 | 2024-10-04 | 2024 | STOCK REPLACEMENT | V-BELT | PLANTGERIA | AWAITING UPDATE WILSON |  | Emeka Okafor
23 | OBOB | LAR-MCTE-283-2024 | 2024-10-04 | 2024 | STOCK REPLACEMENT | V-BELT | PLANTGERIA | AWAITING UPDATE WILSON |  | Emeka Okafor
24 | OB/OB | LAR-MTCE-285-2024 | 2024-10-07 | 2024 | GENERAL SERVICING OF GENERATOR AND REPLACEMENT OF FAULTY PARTS | OIL/AIR/FUEL FILTERS AND LUBE OIL FOR 2540 EG G5-01C | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
25 | OB/OB | LAR-MTCE-286-2024 | 2024-10-07 | 2024 | GENERAL SERVICING OF GENERATOR AND REPLACEMENT OF FAULTY PARTS | OIL/AIR/FUEL FILTERS AND LUBE OIL FOR 4480 EG EG-02 | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
26 | OB/OB | LAR-MTCE-287-2024 | 2024-10-07 | 2024 | STOCK REPLACEMENT | GAS SENSOR FOR ALL TURBINES | INSTRUMENT | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
27 | OBOB | LAR-MCTE-288-2024 | 2024-10-08 | 2024 | RESTORATION OF DAMAGED EMERGENGY FUEL GAS PIPING INTERCONNECT TO 320 PS1 HP SEPARATOR | W.N FLANGE 4'' 600 RJT. SCH 80 MATL: A105, RING JOINT R 37-SOFT IRON MATL: 81-A-105, BALL VALVE 4''X3 RED BORE VB 515-AG ICI…ETC | MECHANICAL | AWAITING QUOTATION |  | Emeka Okafor
28 | IDU | LAR-MCTE-289-2024 | 2024-09-10 | 2024 | FAULTY POWER SUPPLY | POWER SUPPLY 24VDC/5VDC | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
29 | OSHIE FS | LAR-MCTE-290-2024 | 2024-10-13 | 2024 | STOCK REPLACEMENT | 4X35MMSQ 600V ARMORED CABLE, 4X16 MMSQ 600V ARMOURED CABLE AND EXPLOSIONPROOF JUNTION BOX-CLASS I-II | ELECTRICAL | AWAITING QUOTATION |  | Emeka Okafor
30 | EOC | LAR-MTCE-291-2024 | 2024-10-03 | 2024 | MECH SEAL RE-KIT FOR WATER TRANSFER PUMP A IN EOC | MECHANICAL SEAL RE-KITS | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
31 | OBOB | LAR-MCTE-292-2024 | 2024-10-05 | 2024 | TO COMPLETE THE WO ACTIVITY SERIAL NO.240702808 | TAPERED ROLLING BEARING, DEEP GROORE BALL BEARING | MECHANICAL | AWAITING QUOTATION |  | Emeka Okafor
32 | OBOB | LAR-MCTE-293-2024 | 2024-10-12 | 2024 | TRS UNDERGROUND TRANSMISSION CABLE FROM NEWBASE TO EOC | 3X120MMSQ 11KV XPLE CABLE, 3X120MMSQ 11KV STARIGHT THROUGH JOINT KIT(G & W COLD SHRINK JOINTING KITS}, SCOTCH 23 INSULATION TAPE, 120MMSQ CONNECTOR(FERRULE} | ELECTRICAL | AWAITING UPDATE FROM DEPUTY MANAGER ROTATING EQUIPMENT. |  | Ikechukwu Iyeh
33 | OBOB | LAR-MCTE-294-2024 | 2024-10-12 | 2024 | TR6 11KV UNDERGROUND TRANSMISSION CABLE | 3X120MMSQ 11KV XPLE CABLE. | ELECTRICAL | AWAITING UPDATE FROM DEPUTY MANAGER ROTATING EQUIPMENT. |  | Ikechukwu Iyeh
34 | OBOB | LAR-MCTE-295-2024 | 2024-10-11 | 2024 | STOCK REPLACEMENT | GAS CYLINDERS CALIBRATION KIT 2.5% MATHANE UN1956 | PLANTGERIA | AWAITING QUOTATION |  | Emeka Okafor
35 | SAMABIRI | LAR-MCTE-296-2024 | 2024-10-14 | 2024 | TO CARRY OUT GENERAL SERVICING AND RECTIFY FREQUENT HARD STARTING | OIL FILTER, FUEL FILTER AND FUEL SOLENIOD | GMC | QUOTATION SENT FOR APPROVAL |  | Emeka Okafor
36 | OSHIE FS | LAR-MCTE-297-2024 | 2024-10-14 | 2024 | TO CARRY OUT GENERAL SERVICING AND RECTIFY FREQUENT UNDER VOLTAGE/SPEED FLUCTUATIONS | OIL FILTER, LUBE OIL, GAS FILTER, BATTERY 12V, 200AH AND TRANSFORMER T(0-600V) | GMC | QUOTATION SENT FOR APPROVAL |  | Emeka Okafor
37 | EOC | LAR-MCTE-298-2024 | 2024-10-03 | 2024 | MECHANICAL SEAL RE-KIT TO COMPLETE THE MAINTENANCE WO ACTIVITY | MECHANICAL SEAL RE-KITS | MECHANICAL | AWAITING UPDATE FROM DEPUTY MANAGER ROTATING EQUIPMENT. |  | Emeka Okafor
38 | OBOB | LAR-MCTE-299-2024 | 2024-10-12 | 2024 | STOCK REPLACEMENT | V-BELT | GMC | AWAITING QUOTATION |  | Emeka Okafor
39 | KGP | LAR-MCTE-300-2024 | 2024-10-22 | 2024 | REPLACEMENT OF FAULTY DELIVERY PUMP-1 POWER CABLE | 3CX185mm2 ARMOURED CABLE | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
40 | OBOB | LAR-MCTE-301-2024 | 2024-10-22 | 2024 | FOR PLANT USE | PROPANE | GAS PRODUCTION | AWAITING QUOTATION |  | Emeka Okafor
41 | OB/OB | LAR-MTCE-302-2024 | 2024-10-15 | 2024 | SPARE PARTS/MATERIAL AS PER SPECIFICATION TO COMPLETE W/O ACTIVITY AT UNIT 1670 PA-04B PUMP. | MECHANICAL SEAL FLOW -SERVE 1.5 HPX13 SERIAL NO D77085/6 | MECHANICAL FEDOZ | AWAITING QUOTATION |  | Emeka Okafor
42 | IDU FS | LAR-MCTE-303-2024 | 2024-10-24 | 2024 | NO SPARE DETERGENT ZOK-27 FOR CLEANING THE GAS PRODUCER TURBINE BLADES | ZOK-27- GAS TURBINE AND CORROSION INHIBITOR IN JERRYCANS | TURBINE AND ROTATING EQUIPMENT | AWAITING QUOTATION |  | Emeka Okafor
43 | OB/OB | LAR-MTCE-304-2024 | 2024-10-17 | 2024 | SPARE PARTS/MATERIAL AS PER SPECIFICATION TO COMPLETE W/O ACTIVITY AT UNIT 1620 HC-01D AS PER SPECIFICATION | DODGE BEARINGS 402317CM/2162-15/16; DODGE BEARING 124083CM/2162-15/16 | MECHANICAL FEDOZ | AWAITING QUOTATION |  | Emeka Okafor
44 | IDU FS | LAR-MCTE-305-2024 | 2024-10-23 | 2024 | NO SPARE TO REPLACE DAMAGED EXHAUST BLANKET AND HMI FOR TG-B | TURBINE EXHAUST BLANKET AND COMPUTER SYS TT4000SGL | TURBINE AND ROTATING EQUIPMENT | AWAITING QUOTATION |  | Emeka Okafor
45 | EX-ABB CAMP RES. | LAR-MCTE-306-2024 | 2024-10-26 | 2024 | THE LAST SERVICE RUNNING HOURS ON THE 15-03-2024 WAS 1299 HOURS WHILE THE PRESENT RUNNING HOURS IS 1654 | OIL FILTER, FUEL FILTER(PRIMARY0 AND FUEL FILTER(SECONDARY) | GENERATORS | QUOTATION SENT FOR APPROVAL |  | Emeka Okafor
46 | OSHIES F/S | LAR-MCTE-307-2024 | 2024-10-29 | 2024 | GERNERAL SERVICING OF UKPELEDE 500KRGENCYVA GENERETOR IN OSHIE AND REPLACEMENT OF DEAD BATTERIES OF 1000KVA PERKINS EME | SERVICING PARTS, 200AH BATTERY FOR 500KVA UKPELED GEN SET. 200AH BATTERY FOR 100KVA PERKINS EMERGENCY GEN 2 | GENERATORS | AWAITING QUOTATION |  | Emeka Okafor
47 | IRRI FS | LAR-MCTE-308-2024 | 2024-09-22 | 2024 | MATERIALS URGENTLY NEEDED FOR SMOOTH RUNNING OF OPERATIONS | BATTERY 12V-120AH | MECHANICAL | AWAITING QUOTATION |  | Emeka Okafor
48 | IRRI FS | LAR-MCTE-309-2024 | 2024-10-28 | 2024 | TO REPLACE FAULTY PERONI PUMP SEAL | PERONI PUMP SEAL | MACHANICAL | AWAITING QUOTATION |  | Emeka Okafor
49 | EOC | LAR-MTCE-310-2024 | 2024-10-08 | 2024 | STOCK REPLENISHMENT | ADAPTER SLEEVE 60MM BORE - SKF | PLANTGERIA | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
50 | OBOB/EOC/KGP | LAR-MTCE-311-2024 | 2024-10-18 | 2024 | STOCK REPLENISHMENT | BEARING - SKF FOR UNITS 2520 ABC - 56570AB - 520 AD - 1640 AB FAN COOLERS E-MOTORS | PLANTGERIA | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
51 | OSHIE FS | LAR-MCTE-312-2024 | 2024-10-29 | 2024 | MATERIALS REQUIRED FOR CONSTRUTION OF WALK WAY TO NEW CARAVAN AT THE FLOW STATION | M.S PLATE 4F X 8F X5MM THICK, ANGULAR IRON 50MM X 50MMX5MM THK, GALVANIZED PIPE 2'' SCH 40 | TECH OFFICE | AWAITING QUOTATION |  | Emeka Okafor
52 | EOC | LAR-MTCE-313-2024 | 2024-10-29 | 2024 | FLAMME DETECTOR,SENSOR AND VALVE PILOT CONTROL FOR SOLAR TP-1 AND TP-2 | FLAMME DETECTOR,SENSOR AND VALVE PILOT CONTROL FOR SOLAR TP-1 AND TP-2 | TURBINE AND ROTATING EQUIPMENT | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
53 | IDU FS | LAR-MTCE-314-2024 | 2024-10-30 | 2024 | SILICA GEL TO COMPRESS AIR | 30KG SILICA GEL TO COMPRESS AIR | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
54 | OBOB | LAR-MTCE-315-2024 | 2024-11-02 | 2024 | MATERIAL FOR MAINT OF 4690 FV 002 MANUAL VALVE WORK ORDER | SINGLE ROW TAPERED ROLLER BEARING SKL 30211 | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
55 | OSHIE | LAR-MTCE-316-2024 | 2024-11-04 | 2024 | 1855SQMM FERULES AND 92-A6U, 3M, SCOTCHCASTE, CABLE SPLICING KIT FOR 4X185SQMM | 1855SQMM FERULES AND 92-A6U, 3M, SCOTCHCASTE, CABLE SPLICING KIT FOR 4X185SQMM | ELECTRICAL | AWAITING QUOTATION |  | Ikechukwu Iyeh
56 | OBOB | LAR-MTCE-317-2024 | 2024-11-04 | 2024 | TR5/6 11KV, UNDERGROUNG XLPE TRANSMISSION CABLE 3 X 120 mmsq XLPE CABLE, 11KV STRAIGHT THROUGH JOINING KITS | 3 X 120 mmsq XLPE CABLE, 11KV STRAIGHT THROUGH JOINING KITS | ELECTRICAL | DELIVERED AND CLOSED |  | Ikechukwu Iyeh
57 | OBOB EOC | LAR-MTCE-318-2024 | 2024-10-29 | 2024 | STOCK REPLENISHMENT - 530 A B - 360 A B - 2520 A B C FAN COOLERS E-MOTORS | BEARINGS FOR 530 A B - 360 A B - 2520 A B C FAN COOLERS E-MOTORS | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
58 | OSHIE FS | LAR-MTCE-319-2024 | 2024-11-09 | 2024 | CARRY OUT ROUTINE GENERAL SERVICE FOR EMERG GENSET ED - 02 | OIL AND FUEL FILTER FOR PERKINS ENGINE | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
59 | OBOB | LAR-MTCE-321-2024 | 2024-11-13 | 2024 | OBOB PROCESS GAS OPERATIONAL ESSENTIAL MATERIALS | SYSTEM POWER SUPPLY AND OTHER METERING MATS | INSTRUMENT | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
60 | OBOB-EOC-KGP | LAR-MTCE-322-2024 | 2024-11-11 | 2024 | STOCK REPLENISHMENT | AIR BAG / CYLINDRICAL AIR AND CONICAL AIR FILTERS CATRIDGE FOR TUBINES | PLANTGERIA | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
61 | KGP | LAR-MTCE-323-2024 | 2024-11-12 | 2024 | TO FIX FAULTY FIRE PUMP NO. 2 - UNIT 8200 FP2 | GEAR SLEEVE FLEX COUPLING | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
62 | TUOMO | LAR-MTCE-324-2024 | 2024-11-13 | 2024 | BATTERY REPLACEMENT FOR PERKINS GEN - A IN TUOMO | BATTERY 12V-100AH SEALED MAINTENANCE FREE BATTERY | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
63 | OBOB | LAR-MTCE-325-2024 | 2024-11-16 | 2024 | NGL AND HSE AREA AIR CONDITIONER | 32A, 4POLE DIFF CIRCUIT BREAKER, ARMOURED CABLE AND ACCESSORIES | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
64 | OBOB | LAR-MTCE-326-2024 | 2024-11-16 | 2024 | PMS DESK AREA AIR CONDITIONER REPAIRS | 32A, 4POLE DIFF CIRCUIT BREAKER, ARMOURED CABLE AND ACCESSORIES | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
65 | OBOB | LAR-MTCE-327-2024 | 2024-11-10 | 2024 | SEAL KITS FOR MECHANICAL SEAL ASSEMBLE AT THE 1600-PA-07 | REPAIR KITS - Q28KM | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
66 | OBOB | LAR-MTCE-328-2024 | 2024-11-10 | 2024 | MATERIAL FOR PUMP ASSEMBLY AT THE 1600-PA-07 | COMPLETE ASSEMBLED MECH SEAL - MATERIAL - Q28KM | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
67 | OBOB | LAR-MTCE-329-2024 | 2024-11-16 | 2024 | MATERIALS FOR UNIT 1300 SWITCHGEAR AIR CONDITIONER | 32A, 4POLE DIFF CIRCUIT BREAKER, ARMOURED CABLE AND ACCESSORIES | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
68 | OBOB | LAR-MTCE-330-2024 | 2024-11-30 | 2024 | STOCK REPLENISHMENT | PRESSURE SWITCH 4-200PSI FOR UNIT 1640ABC | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
69 | OBOB | LAR-MTCE-331-2024 | 2024-12-02 | 2024 | STOCK REPLENISHMENT | MOTOR CIRCUIT BREAKER FOR 2540 ABC AND 1640 ABC | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
70 | OBOB | LAR-MTCE-332-2024 | 2024-12-01 | 2024 | STOCK REPLENISHMENT | OVERLOAD RELAYS - SIEMENS FOR 2540 ABC; 4540 DE; 1640 ABC AND 470 GT 1/2 | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
71 | OBOB | LAR-MTCE-333-2024 | 2024-11-30 | 2024 | STOCK REPLENISHMENT | THREE POLE BREAKER FOR 2520 ABC; 2570 AB; 520 CD AND 1640 ABC | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
72 | OBOB | LAR-MTCE-334-2024 | 2024-11-30 | 2024 | STOCK REPLENISHMENT | CONTACTORS FOR 2520 ABC AND 4520 DE | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
73 | OBOB | LAR-MTCE-337-2024 | 2024-12-04 | 2024 | TO REPLACE MECH SEALS | LEAKING MECH SEAL AT KWALE 6100 BP 701 PUMP | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
74 | IRRI | LAR-MTCE-338-2024 | 2024-11-23 | 2024 | AIR COMPRESSOR UNIT 460-MKC-01B | ATLAS COPCO AIR FILTER | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
75 | KWALE | LAR-MTCE-339-2024 | 2024-12-03 | 2024 | TO REPLACE MECH SEALS AT KWALE GAS PLANT | LEAKING MECH SEAL AT KWALE 6100 BP 702 PUMP | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
76 | KWALE | LAR-MTCE-340-2024 | 2024-12-02 | 2024 | STOCK REPLENISHMENT | GEAR SLEEVE FLEX COUPLING FOR FIRE PUMP UNIT 8200 FP2 | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
77 | KWALE | LAR-MTCE-341-2024 | 2024-12-02 | 2024 | STOCK REPLENISHMENT | PRESSURE TRANSMITTER FOR 710-PT-01A | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
78 | KWALE | LAR-MTCE-342-2024 | 2024-11-29 | 2024 | HVAC DRAIN VALVE REPLACEMENT | 1/2" DRAIN VALVE FOR 610 AIRTENT | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
79 | OBOB | LAR-MTCE-343-2024 | 2024-11-29 | 2024 | STOCK REPLENISHMENT FOR FAN COOLER E-MOTOR | PULLEY WITH TAPER LOCK FOR 1670-HC-01A | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
80 | OBOB | LAR-MCTE-344-2024 | 2024-12-07 | 2024 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT 1620-HC-FAN COOLERS | HTD-3500-FAN BELT: HTD 3500 | MECHANICAL | MRF PROCESS IS ONGOING |  | Emeka Okafor
81 | OBOB | LAR-MCTE-345-2024 | 2024-12-07 | 2024 | TO COMPLETE CORRECTIVE MAINTENANCE WORK ORDER AT 1670-HC-FAN COOLERS | SPB 4500-FAN BELT: SPB 4500 | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
82 | IRRI | LAR-MCTE-346-2024 | 2024-12-12 | 2024 | MATERIAL AS PER SPECIFIED IS TO USE TO COMPLETE CORRECTIVE MAINTENANCE W/O AT THE IRRI JOCKEY PUMP | MECHANICAL SEAL | MECHANICAL | MRF PROCESS IS ONGOING |  | Emeka Okafor
83 | OSHIE | LAR-MCTE-348-2024 | 2024-12-17 | 2024 | TO REPLACE CUT FAN BELT OF OSHIE 500KWA CAT GEN. | FAN BELT, ALTERNATOR FAN BELT | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
84 | OBOB | LAR-MCTE-349-2024 | 2024-12-17 | 2024 | FOR THE REPAIR AND RESTORATION OF THE XPLE ARMORED CABLE | 3X120SQMM, 11KV, XPLE ARMOURED CABLE, 11KV 3 CORE G&W CABLE SPLICING KIT, 120SQMM FERRULES …ETC | ELECTRICAL | MRF PROCESS IS ONGOING |  | Ikechukwu Iyeh
85 | OBOB | LAR-MCTE-350-2024 | 2024-12-17 | 2024 | FOR THE REPAIR AND RESTORATION OF SERVICE YARD SUMO POWER CABLE | LOW VOLTAGE CABLE SPLICING KIT 92-A2 | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
86 | OBOB | LAR-MCTE-351-2024 | 2024-12-16 | 2024 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT THE EASTLINE PUMP | TO CHANGE BATTERIES OF EASTLINE PUMP | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
87 | IDU | LAR-MCTE-352-2024 | 2024-12-23 | 2024 | TO COMPLETE CORRECTIVE MAINTENANCE WORK AT IDU AIR COMPRESSOR | SILICA GEL | MECHANICAL | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
88 | OBOB | LAR-MCTE-353-2024 | 2024-12-23 | 2024 | TO REPLACE FAILED SUBCIRCUIT BREAKER IN EOC NEW SWITCH GEAR | CIRCUIT BREAKER, ABB SACE TMAX: TYPE =XT2S 160, 4POLES | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
89 | KWALE | LAR-MCTE-354-2024 | 2024-12-24 | 2024 | TO REPLACE FAULTY ALTRONIC IGNITION SYSTEM ON THE DRIVER UNIT OF 5100 COMPRESSOR | ALTRONIC IGNITION, S/N: 76294 | GENERATORS SPARES | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
90 | OBOB | LAR-MCTE-355-2024 | 2024-12-26 | 2024 | TO REPLACE FAULTY SUMO PUMPS IN OBOB GAS PLANT | 25HP-18.6KW, 3PH34-36A, 50HZ SUBMERSIBLE PUMP. MAKE -GROUNDFOS | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
91 | OBOB | LAR-MCTE-356-2024 | 2024-12-31 | 2024 | TO TEST RUN NEW PORTABLE MOBILE AIR CONDITIONER FOR INDUSTRIAL LAB USAGE IN NEW BASE | METERIALS: ELBOW 1/2X3000, UNION 1/2 X3000, EQUAL TEE 1/2…ETC | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
92 | OBOB | LAR-MTCE-400-2024 | 2024-12-02 | 2024 | STOCK REPLENISHMENT | BEARINGS FOR 2540 ABC; 4540 DE; TG 1/2 | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor
93 | OBOB | LAR-MCTE-402-2024 | 2024-11-30 | 2024 | TO REPAIR VANDALIZED OLD GCAPA YARD POWER SUPPLY CABLE | 4X25SSQMM, 600/100V, PVC INSULATED ARMORED CABLE NIGERCHIN, 91-A2, 3M, SCOTCHCASTE, CABLE SPLICING KIT, 25SQMM FERRULES | ELECTRICAL | AWAITING UPDATE FROM IYEH
94 | OBOB | LAR-MTCE-403-2024 | 2024-12-02 | 2024 | HVAC DRAIN VALVE REPLACEMENT | ELECTRONIC CONTROL MODEL FOR GENSET 2206 A 350KVA | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
95 | OBOB | LAR-MTCE-404-2024 | 2024-12-02 | 2024 | STOCK REPLENISHMENT TO MAINTAIN MIN SPARES | DCS SPARES FOR UNIT 970 IN OBOB | ROT EQUIP | AWAITING UPDATE FROM EMEKA |  | Emeka Okafor