## Sheet1
S/N | LOCATION | MRF NUMBER | REQUEST DATE | YEAR | REASON FOR REQUEST | SERVICE\MATERIAL | DISCIPLINE | MRF STATUS | CONTRACT / CALL OFF NO | REMARKS
1 | BRASS | SAR-071-2024 | 2024-08-28 | 2024 | REPLACEMENT OF FAULTY 3no. SUBMERSIBLE PUMPS | 4 X 4mm BLACK FLEXIBLE CABLE IN MTRS AND SCOTCH CAST RESIN KITS | ELECTRICAL | AWAITING QUOTATIONS |  | Ikechukwu Iyeh
2 | BRASS | SAR-072-2024 | 2024-09-01 | 2024 | REPLACEMENT OF CORRODED Z-PURLINS FOR HSE BUILDING FIRE TRUCK BAY | LONG ZEDS PURLINS; RED OXIDE PAINT; THINNER & BRUSHES | MAINTENANCE | AWAITING QUOTATIONS |  | Emeka Okafor
3 | BRASS | SAR-073-2024 | 2024-09-02 | 2024 | REPLACEMENT OF RESIDENTIAL EDG VOLTAGE RHEOSTAT | VOLTAGE RHEOSTAT - CAT | ELECTRICAL | AWAITING QUOTATIONS |  | Ikechukwu Iyeh
4 | OBAMA F/S | SAR-074-2024 | 2024-09-02 | 2024 | SERVICING PARTS FOR OBAMA FLOW STATION CG-2 | LUBE OIL NEGECO ADVANCE 40 CAT OIL & HEAVY DUTY CAT BATTERY | MAINTENANCE | AWAITING QUOTATIONS |  | Emeka Okafor
5 | BRASS TERMINAL | SAR-075-2024 | 2024-09-03 | 2024 | REPLACEMENT OF PUMP | MECHANICAL SEAL SPARES | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
6 | BRASS TERMINAL | SAR-076-2024 | 2024-09-03 | 2024 | REPLACEMENT OF FAILED INSTRUMENT POWER CABLE AND SPARE | DELTA-V 24/12 VDC ENHANCED POWER SUPPLY DC/DC PASS THROUGH CABLE | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
7 | BRASS TERMINAL | SAR-077-2024 | 2024-09-07 | 2024 | REPLACEMENT OF INDUSTRIAL EDG FAN BELTS | FAN BELTS | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
8 | BRASS TERMINAL | SAR-078-2024 | 2024-09-07 | 2024 | REPLACEMENT OF BAD KICK STARTER FOR PORTABLE ANGUS FIRE PUMP | KICK STARTER | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
9 | BRASS TERMINAL | SAR-079-2024 | 2024-09-08 | 2024 | REPLACEMENT OF WEAK BATTERIES FOR BRASS EDG AND START/STOP SWICTHES FOR BOTH BRASS EDG MCC AND CLOUGH CREEK JOCKEY PUMP- 2 | START/STOP SWICTH AND 12V 200 AH CAT | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
10 | CLOUGH CREEK | SAR-080-2024 | 2024-09-08 | 2024 | REPLACEMENT OF SERVICING PARTS FOR EDG -C32 | OIL, FUEL FILTERS, WATER SEPARATOR AND LUBE OIL | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
11 | OGBOINBIRI | SAR-081-2024 | 2024-09-10 | 2024 | MATERIAL REPLACEMENT FOR TRU-FLO PUMP AT RECOVERY PIT | COMPLETE TRUFLO MECHANICAL SEAL STYLE 770FFD01 - SEALTEK | MAINTENANCE | AWAITING UPDATE EMEKA |  | Emeka Okafor
12 | BRASS TERMINAL | SAR-083-2024 | 2024-09-22 | 2024 | MATERIALS REQUIRED FOR URGENT ELECTRICAL CONSUMABLES IN SAR | 18W LED BULB, E27 CERAMIC LAMP HOLDER, 11 W LED BULB…ETC | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
13 | CLOUGH CREEK | SAR-084-2024 | 2024-09-22 | 2024 | MATERIALS REQUIRED FOR SERVICING PARTS FOR CLOUGH CREEK EDG | SEVICING PARTS, WATER SEPAATOR AND SAE 40 LUBE OIL | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
14 | OBAMA F/S | SAR-085-2024 | 2024-09-22 | 2024 | MATERIALS TO REPLACE GRP GENERATOR FUEL PUMP. | 12V FUEL PUMP | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
15 | BRASS | SAR-086-2024 | 2024-10-17 | 2024 | REPLACEMENT OF OF BURNT HELIPAD PERIMETER SURFACE FLOOD LIGHT | DOWNING SEALED BEAM HELIPAD SURFACE FLOOD LAMP 24VAC, 100VA CONTROL TRANFORMER INPUT 220VAC OUTPUTAC FREQUENCY 50HZ | ELECTRICAL | AWAITING QUOTATION |  | Ikechukwu Iyeh
16 | BRASS | SAR-087-2024 | 2024-10-13 | 2024 | REPLACEMENT OF SPARK PLUGS FOR RCE GENERATORS | SPARK PLUGS | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
17 | OGBOINBIRI | SAR-088-2024 | 2024-10-10 | 2024 | NON IN STOCK | MECHANICAL SEAL, BEARING | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
18 | BRASS TERMINAL | SAR-089-2024 | 2024-10-13 | 2024 | SPARK PLUG FOR RCE GENERATORS REPLACEMENT | SPARK PLUGS | MAINTENANCE | AWAITING UPDATE |  | Ikechukwu Iyeh
19 | BRASS | SAR-090-2024 | 2024-10-13 | 2024 | REPLACEMENT OF BADLY DAMAGED CITADEL FENCES | GALVANIZED CITADEL FENCE WIRE MESH | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
20 | CLOUGH CREEK | SAR-091-2024 | 2024-10-13 | 2024 | REPLACEMENT OF EDG BAD ALTERNATOR BELT BATTERIES | ALTERNATOR V-BELT, CAT BATTERRY 12V, 190 AH | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
21 | BRASS | SAR-092-2024 | 2024-10-16 | 2024 | URGENT MATERIALS NEEDED TO AVOID CRUDE OIL LOADING DELAY IF THE ONE REMAINING FAILS | PAKSCAN MASTER STATION CLASSIC CHASSIS, MODEL NUMBER: PS710, OPTIMAL PAKSCAN IIE CURRENT LOOP MODULE | MAINTENANCE | AWAITING update from Barry/Metering supervisor |  | Emeka Okafor
22 | BRASS | SAR-093-24 | 2024-10-17 | 2024 | REPALCEMENT OF BURNT HELIPAD PERIMETER SURFACE FLOOD LIGHT | DOWNING SEALED BEAM HELIPAD SURFACE FLOOD LAMP 24VAC, 100VA CONTROL TRANFORMER INPUT 220VAC OUTPUTAC FREQUENCY 50HZ | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
23 | OGBOINBIRI | SAR-094-2024 | 2024-10-19 | 2024 | VERY URGENT PRESSURE GUAGES FOR MAINTENANCE USE | 0-60PSI, 0-2.5KG/CM2, 0-4KG/CM2, 0-10PSI…ETC | MAINTENANCE | AWAITING UPDATE FROM DEP. MANAGER ROTATING EQUIPMENT |  | Emeka Okafor
24 | BRASS TERMINAL | SAR-095-2024 | 2024-10-21 | 2024 | REPLACEMENT OF FAULTY TOWER LIGHT LAMPS AND FITTINGS | TOWER LIGHTS, BOOSTER LIGHTS POER STATION LIGHTS…ETC | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
25 | OGBOINBIRI | SAR-097-2024 | 2024-10-23 | 2024 | MATERIALS REPLACEMENT GAS COMPRESSOR AND GTG-B | POWER SUPPLY FOR THE PLC RACK ON LP/MP-A, SOLENIOD VALVES FOR COMPRESSOR UNITS, ELECTRIC FAN MOTOR FOR GTG-B …ETC | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
26 | BRASS TERMINAL | SAR-098-2024 | 2024-10-23 | 2024 | REPLACEMENT OF BURNT CONTACTOR AT THE RESIDENTIAL FIREFIGHTING SYSTEM | ABB A40-30 CONTACTOR, AUXILLARY CONTACT | ELECTRICAL | AWAITING QUOTATION |  | Ikechukwu Iyeh
27 | OBAMA F/S | SAR-099-2024 | 2024-10-26 | 2024 | REPLACEMENT OF SERVICING PARTS | LUBE OIL (CAT NGEO ADVANCED 40) -400L, OIL FILTERS (CAT) | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
28 | CLOUGH CREEK | SAR-100-2024 | 2024-10-27 | 2024 | REPLACEMENT OF SERVICING PARTS | LUBE OIL (DEO 15W- 40) 200L, OIL FILTERS,FUEL FILTER, WATER SEPARATOR (CAT) | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
29 | BRASS TERMINAL | SAR-101-2024 | 2024-10-28 | 2024 | REPLACEMENT OF REMOVED RADIATOR FAN MOTOR FOR RCE GENERATORS | RADIATOR FAN MOTOR. | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
30 | TEBIDABA F/S | SAR-102-2024 | 2024-11-05 | 2024 | MATERIALS REQUIRED FOR TEBIDABA DELIVERY PUMP 2 | METEFLEX COUPLING COMPLETE SIZE -80-200/147 WITH PILOT BORE M-60MM (DRG NO 80-200-140.16/ S.NO-34366/1) | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
31 | BRASS TERMINAL | SAR-103-2024 | 2024-10-05 | 2024 | MATERIALS REQUIRED FOR FIRE FIGHTING PUMP, DRAINSUMP P16A AND TANK 19 DRAIN PUMP. | 1) A40-30, 240V, 1EAC=60A 11 KW CONTACTOR -4 PCS 2) BEARING 6307 -4PCS | MAINTENANCE | AWAITING QUOTATION |  | Emeka Okafor
32 | BRASS TERMINAL | SAR-104-2024 | 2024-10-10 | 2024 | MATERIALS REQUIRED TO REPLACE LEAKING WATER HOSE ON GEN - 3 | HOSE PIPE | MAINTENANCE | AWAITING QUOTATION |  | Ikechukwu Iyeh
33 | BRASS TERMINAL | SAR-105-2024 | 2024-11-15 | 2024 | MATERIALS FOR REACTIVATION OF TEST SEPARATOR AT TEBIDABA STATION | VARIOUS VALVES, TRANSMITTERS AND FITTINGS | MAINTENANCE | MRF APPROVED |  | Emeka Okafor
34 | BRASS TERMINAL | SAR-106-2024 | 2024-11-15 | 2024 | MATERIALS FOR REACTIVATION OF TEST SEPARATOR AT OBAMA STATION | VARIOUS VALVES, TRANSMITTERS, DOB, BARTON RECORDER AND FITTINGS | MAINTENANCE | MRF APPROVED |  | Emeka Okafor
35 | BRASS TERMINAL | SAR-107-2024 | 2024-11-17 | 2024 | MATERIALS FOR RESTORATION OF OBAMA CG - 2 | AVR VR6 AND POTENTIAL TRANSFORMER (PT) | ELECTRICAL | AWAITING UPDATE FROM IYEH |  | Ikechukwu Iyeh
36 | OGBOINBIRI GAS PLANT | SAR-108-2024 | 2024-11-23 | 2024 | MATERIALS FOR REPLACEMENT OF FAULTY I/P CONVERTER, TRANSMITTER ON THE SEPERATORS, VESSELS AND CONTROL VALVES | I/P CONVERTER HART; SOLENOID VALVES; OIL LEVEL TRANSMITTER AND LIMIT SWITCHES / VALVE POSITIONER | ELECTRICAL | AWAITING FEEDBACK FROM VENDOR |  | Ikechukwu Iyeh
37 | OGBOINBIRI GAS PLANT | SAR-109-2024 | 2024-11-24 | 2024 | MATERIALS FOR REPLACEMENT OF FAULTY TURBOCHARGER, KICKSTARTER | TURBOCHARGER, KICKSTARTER AND HEAVY DUTY BATTERIES FOR FIRE PUMP A AND B IN OGBOINBIRI GAS PLANT | MAINTENANCE | ROT EQUIP ACTION |  | Emeka Okafor
38 | BRASS TERMINAL | SAR-110-2024 | 2024-11-22 | 2024 | MATERIALS REQUIRED FOR DCS MONITOR AND PROTECTION SYSTEM FOR SLUDGE TRANSFER PUMP 3A AND 3C | FITTINGS SWAGELOK AND ROSEMOUNT TRANSMITTERS AND CABLE | MAINTENANCE | MRF APPROVED |  | Emeka Okafor
39 | BRASS TERMINAL | SAR-111-2024 | 2024-11-24 | 2024 | MATERIALS REQUIRED FOR DCS MONITOR AND PROTECTION SYSTEM FOR SLUDGE TRANSFER PUMP 3B | FITTINGS SWAGELOK AND ROSEMOUNT TRANSMITTERS AND CABLE | MAINTENANCE | MRF APPROVED |  | Emeka Okafor
40 | BRASS TERMINAL | SAR-112-2024 | 2024-11-24 | 2024 | MATERIALS FOR REOPENING OF OGBOINBIRI DEEP 3T | WN REDUCER AND EQUAL TEE | MAINTENANCE | ON GOING AVAILABILITY CHECK |  | Emeka Okafor
41 | BRASS TERMINAL | SAR-113-2024 | 2024-11-28 | 2024 | RESTORATION OF FAULTY PRESSURE SAFETY VALVES(PSVs) | DIFERENT TYPES OF PRESSURE SAFETY VALVES | INSTRUMENT | AWAITING QUOTATION |  | Emeka Okafor
42 | TEBIDABA | SAR-114-2024 | 2024-11-29 | 2024 | TO SERVICE TEST SEPARATOR DANIEL ORIFICE BOX(DOB) | 20L MULTI-PURPOSE GRESE, WD-40 ANTI-RUST SPRAY, KLINGER PAPER GASKET….ETC | INSTRUMENT | AWAITING QUOTATION |  | Emeka Okafor
43 | OBAMA | SAR-115-2024 | 29-NOV.24 | 2024 | TO FIX 14'' TEST SEPARATOR DANIEL ORIFICE BOX (DOB) | 14'' DOB PLATE CARRIER, 14'' DOB PLATE HOLDER AND DOB GREASER | INSTRUMENT | AWAITING QUOTATION |  | Emeka Okafor
44 | OBAMA | SAR-116-2024 | 2024-11-30 | 2024 | TO REPLACE FAULTY FIRE PUMP CHECK VALVE | 8'' X 150 CHECK VALVE | MECHANICAL | AWAITING QUOTATION |  | Emeka Okafor
45 | OGBOINBIRI | SAR-117-2024 | 2024-12-04 | 2024 | MATERIALS | LED BULB 15 WATT E 27 6500K 220V, PHILLIPS SMART BRIGHT WATERPROOF BATTEN 16.5W, 1800 LUMEN(2FT)….ETC | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
46 | OBAMA | SAR-118-2024 | 2024-12-03 | 2024 | TO REPLACE VANDALIZED CCU / CHOKE BOX AT PIRI-2T IN OBAMA F/S | CCU AND CHOKE BOX 2 1/16" X 10,000 | MECHANICAL | ON GOING AVAILABILITY CHECK |  | Emeka Okafor
47 | OGBOINBIRI GAS PLANT | SAR-119-2024 | 2024-12-09 | 2024 | SERVICING OF INSTRUMENT AIR COMPROSSORS(STATIONARY AND MOBILE) | SERVICING KIT FOR MOBILE AIR COMPRESSOR XHAS 186(1000 HOURS), SERVICING KIT FOR STATIONARY AIR COMPRESSORR ZT30(OLD), ROTO Z | INSTRUMENT | AWAITING UPDATE EMEKA |  | Emeka Okafor
48 | OGBOINBIRI GAS PLANT | SAR-120-2024 | 2024-12-09 | 2024 | SERVICING KIT FOR EMERGENCY GENEATOR(EDG) | OIL FILTER, DIESEL FILTER, LUBE FILTER, ENGINE OIL AND ECO-II AIR FILTER(MODULE-ECO-II 13 5X24 1 1 | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
49 | BRASS TERMINAL | SAR-121-2024 | 2024-12-03 | 2024 | TO REPLACE BAD BATTERIES FOR PRODUCTION GENEERATORS AND FIRE PUMPS AT BRASS AND FLOW STATIONS IN ORDER TO CLEAR PENDING UNSAFE CONDITIONS | 101-4000, 12V, PREMIUM HIGH OUTPUT, DRY BATEERY. 12V 52AH, 20HR BATTERY …ETC | ELECTRICAL | AWAITING UPDATE IYEH |  | Ikechukwu Iyeh
50 | OBAMA | SAR-122-2024 | 2024-12-04 | 2024 | RING JOINT FOR 8'' BALL VALVE FOR OBAMA | RING JOINT | INSTRUMENT | DELIVERED |  | Emeka Okafor
51 | OGBOINBIRI | SAR-123-2024 | 2024-12-17 | 2024 | MATERIAL REPLACEMENT FOR NEW SULZER PUMP C | SPACER COUPLING | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
52 | CLOUGH CREEK | SAR-124-2024 | 2024-12-20 | 2024 | SERVICING OF EMERGENCY GENERATOR | OIL9DEO-15W40), OIL FILTERS, WATER SEPARATOR FILTER AND FUEL FILTER | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
53 | OBAMA | SAR-125-2024 | 2024-12-20 | 2024 | SERVICING OF COMMUNITY GENERATOR(CG2) AT OBAMA F/S | OIL{NGEO ADVANCE 40}, OIL FILTERS AND ENGINE COOLANT | MECHANICAL | AWAITING UPDATE IYEH |  | Emeka Okafor
54 | BRASS TERMINAL | SAR-126-2024 | 2024-12-24 | 2024 | REVAMPING AND UPGRADE OF BRASS TERMINAL 3KA MV SWITCH GEAR | 1.5MM SINGLE STARNDED CABLE | ELECTRICAL | CONTRACT NUMBER ASSIGNED |  | Ikechukwu Iyeh
55 | OGBOINBIRI GAS PLANT | SAR-127-2024 | 2024-12-24 | 2024 | MATERIAL REPLACEMENT FOR DIESEL FIRE PUMPS | MAXMECH HEAVY DUTY CAR BATTERY CHARGER 12V/24V PORTABLE BOOSTER 650A | MECHANICAL | AWAITING UPDATE EMEKA |  | Emeka Okafor
56 | OBAMA | SAR-128-2024 | 2024-12-28 | 2024 | TO REPLACE FAULTY LEVEL TRANSMITTER AT OBAMA FLOWSTATION | MASONEILAN LEVEL TRANSMITTER. | INSTRUMENT | AWAITING UPDATE EMEKA |  | Emeka Okafor