## Sheet1
S/N | LOCATION | MRF NUMBER | REQUEST DATE | YEAR | REASON FOR REQUEST | SERVICE\MATERIAL | DISCIPLINE | STATUS NOTES | COMPANY | CALL OFF NUMBER | REMARKS
1 | OGBOINBIRI | PHC-204-2025 | 2025-01-21 | 2025 | QUOTATION FOR THE MATERIALS REQUIRED TO CONSTRUCT THE OIL COOLING LINES FOR THE OLD SULZER PUMP B & C | PUMPS | MECHANICAL |  |  | Material delivered, CLOSED
2 | OGBOINBIRI | PHC-205-2025 | 2025-01-21 | 2025 | QUOTATIONS FOR MATERIALS REQUIRED FOR RESTORATION/REFURBISHMENT OF TRUFLO PUMP | PUMPS | MECHANICAL |  |  | Quotation pending with DODM
3 | IDU | PHC-207-2025 | 2025-03-20 | 2025 | QUOTATION FOR SULZER TP2 PUMP MAJOR REFURBISHMENT AND RESTORATION AT IDU | SULZER TP2 PUMP | MECHANICAL |  |  | QUOTATION PENDING APPROVAL
4 | AKRI | PHC-211-2025 | 2025-02-23 | 2025 | MATERIALS FOR THE SHUTDOWN VALVE MAINTENANCE JOBS AT AKRI FLOW STATION | R-23RJT GASKET, 12''X900 RJT BLINDS, 2''X300# SPIRAL WOUND GASKET….ETC | MECHANICAL |  |  | AWAITING UPDATE FROM EMEKA
5 | PHC | PHC-212-2025 | 2025-03-03 | 2025 | MATERIALS FOR THE SHUT DOWN VALVE MAINTENANCE INTERVENTION AT AKRI F/S | 4''X 600# RF GASKET, 6" X 300# SPIRAL WOUND GASKET…ETC | MECHANICAL |  |  | AWAITING UPDATE FROM EMEKA
6 | PHC | PHC-213-2025 | 2025-03-16 | 2025 | URGENT PROCUREMENT OF SPHERIOD FOR BRASS AND EOC | PHERIOD F | MECHANICAL |  |  | AWAITING QUOTATION | CHUKWU DANIEL
7 | OGBOINBIRI | PHC-214-2025 | 2025-04-03 | 2025 | QUOTATION FOR RESTORATION & CORRECTIVE MAINTENANCE OF SULZER OLD PUMP B AT OGBAINBIRI | PUMPS | MECHANICAL |  |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
8 | SAMABIRI | PHC-215-2025 | 2025-04-16 | 2025 | QUOTATION FOR MATERIALS REQUIRED FOR THE STATUTORY INSPECTION OF SAMABIRI | MATERIALS FOR INSPECTION | MECHANICAL |  |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
9 | IDU | PHC-216-2025 | 2025-04-16 | 2025 | QUOTATION FOR MATERIALS REQUIRED FOR THE STATUTORY INSPECTION OF IDU F/S | MATERIALS FOR INSPECTION | MECHANICAL |  |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
10 | EBOCHA | PHC-217-2025 | 2025-04-29 | 2025 | QUOTATION FOR THE PRCURUEMENT OF SPARES FOR THE REFURBISHMENT AND RESTORATION OF FINDER TANK BOOSTER PUMP A | TANK BOOSTER PUMP A | MECHANICAL |  |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
11 | PHC | PHC-218-2025 | 2025-07-28 | 2025 | SHUTDOWN MATERIALS REQUIRED FOR THE STATUTORY INSPECTION OF SAMABRI | SPIRAL WOUND GASKET 14" 300# RF, RING JOINT R39 SOFT IRON | MECHANICAL |  |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
12 | PHC | PHC-220-2025 | 2025-05-27 | 2025 | MATERIAL REQUEST FOR MAINTENANCE OF PH BASE RESIDENTIAL EDG | SPEED CONTROL, 415V, 50/60Hz | ELECTRICAL |  |  | QUOTATION PENDING APPROVAL | IKECHUKWU IYEH
13 | PHC | PHC-221-2025 | 2025-06-03 | 2025 | MATERIAL REQUEST FOR THE ROUTINE MAINTENANCE SPARES FOR PH BASE EDG'S AND MODULE FOR 30KVA POWERHOUSE EDG, CONTROL MODULE FOR 165 KVA CLINIC EDG | WATER SEPARATOR, RACLE FILTER, FUEL FILTER, OIL FILTER ….ETC | ELECTRICAL |  |  | QUOTATION PENDING APPROVAL | IKECHUKWU IYEH
14 | PHC | PHC-223-2025 | 2025-06-30 | 2025 | MATERIAL REQUEST FOR THE REPLACEMENT OF RESIDENTIAL 1000KVA EDG FAN BELT | FAN BELT | MECHANICAL |  |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
15 | PHC | PHC-224-2025 | 2025-08-28 | 2025 | MATERIAL REQUEST FOR THE CORRECTIVE MAINTENANCE OF EARTHING AND LIGHTING PROTECTION SYSTEM IN OBOB GAS PLANT | ELECTRO ATMOSPHERIC FIELD PROTECTOR, MONITORING DEVICE storm 7, EXTERNAL SHELTER FOR MONITORING DEVICE…..ETC | ELECTRICAL |  |  | QUOTATION PENDING APPROVAL | IKECHUKWU IYEH
16 | PHC | PHC-225-2025 | 2025-08-09 | 2025 | EBOCHA GUN BARREL PIPING MODIFICATION PROJECT | H-Beam (100 x 100 x 5 x 12m), Anchor/ expansion Bolts/ Civil works materials, 14'' x 12m Pipe CS Sch 80…......ETC | ELECTRICAL |  |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
17 | PHC | PHC-234-2025 | 2025-11-08 | 2025 | MATERIAL REQUEST FOR THE MAINTENANCE OF EARTHING AND LIGHTING PROTECTION SYSTEM IN BRASS TANK FARM | CABLE LUG. - 70MM X M12 HOLE COPPER, M12 X 40MM S.S BOLT & NUT WITH FLAT & SPRING WASHER, HEAVY DUTY GREASE (20 LTRS)…ETC | ELECTRICAL |  |  | QUOTATION PENDING APPROVAL | EMEKA OKAFOR
18 | PHC | PHC-235-2025 | 2025-11-11 | 2025 | MATERIAL REQUEST FOR THE MAINTENANCE OF EARTHING AND LIGHTING PROTECTION SYSTEM IN OGB GAS PLANT | copper Nuts, Bolts and Washers, Heavy Duty Grease 4 ltrs, 6meter 50mm GI monopole & mounting brackets…...ETC | ELECTRICAL